## CAP
Repeat | SubformId | Benchmark ID | Benchmark details | Finding details | Recommendation for Immediate Action | Company Plan of Action | Company deadline | Action Taken | Company Progress Status | Repeat
Ongoing
|  |  |  | Member(s) | Outerstuff LLC |  |  |  |  | Option 3
|  |  |  | Country | Philippines |  |  |  |  | Option 4
|  |  |  | Date of Inspection | 2024-08-07 |  |  | VIEW:VW_report_CAPaction for action table | Planned | Option 5
|  |  | ID |  |  |  |  | hiddenfields for import | In Progress
Additional CAP Notes
|  | Benchmark ID and details | Question(s) and findingdetails | Recommendation for Immediate Action | Recommendation for Sustainable Improvement | Company Plan of Action | Company deadline (MM-DD-YYYY) | Action Taken | Company Progress Status
| 9566 | C.21.2-All benefits shall be calculated correctly | Are all benefits calculated correctly? - (1) The factory's holiday pay rate for piece rate workers is not properly calculated under local wage laws. The facility does not calculate these workers' average earnings of the 7 days prior to the holiday and pay that amount as required. Instead the factory pays the minimum wage. (2) The facility requires workers who are single parents and eligible for parental leave benefits to provide a reason specific to the child when filing for this leave benefit. Under local law eligible workers should access this leave the same way they do other paid leaves. | (1) Ensure that holiday pay for piece rate workers is not less than the worker's average daily earnings for the 7 work days preceding the holiday and that the holiday pay is not less than the applicable statutory minimum wage rate in any case. (2) Provide parental leave when the worker fulfills eligibility without any restrictions. |  |  |  | Closed. ALL AMOUNTS BEEN REVIEWED AND AMENDED | Completed
| 9567 | C.3.1.3-Where probationary employment is legally allowed no workers shall work more than three months in this employment category. | In all cases has the cumulative probation period of trainees and/or probationary workers been strictly limited to three months or less? - Newly hired workers undergo 5-6 months of probation period instead of the 3 months' maximum set by the FLA Code. Factory management explained that local law allows for up to 6 months' probationary period. | Ensure the probation periods are not more than three months as per FLA Code. |  |  |  | Completed | Completed
| 9568 | ER.1.2-Employers shall assign responsibility for the administration of human resources to a clearly defined and adequately qualified staff member or staff members and ensure workers at all levels receive communication and training about existing policies and procedures or any revisions. | Does the factory provide any ongoing training to workers on all FLA's Code elements and Employment Functions? - The ongoing training for workers does not include freedom of association/collective bargaining or environmental protection. |  |  |  |  | Completed. EACH DEPARTMENT HAS A GRIEVANCE BOARD MEMBER | Completed
| 9569 | ER.1.3-Employers should implement an annual review process with input from workers of all policies procedures and their implementation to ensure they meet legal requirements and the FLA Workplace Code. | Are the factory's policies and procedures on all FLA's Code elements and Employment Functions regularly reviewed?Are workers consulted or integrated in the decision-making process of aspects concerning workplace and working conditions (e.g. creation or revision of policies and procedures changes on production processes hours of work etc.)? - (1) The factory's policies and procedures are not regularly reviewed and updated. (2) The factory has not established procedures to request and/or receive workers’ input/feedback regarding the creation implementation and updating of its policies and procedures. Workers are neither systematically integrated nor consulted in decision-making processes. |  |  |  |  | In Process. WILL COMPLETE 1-30-25 | In Progress
| 9570 | ER.17.2-There shall be a mechanism that allows workers to report harassment and grievances confidentially including any concerns or problems they may be experiencing around legally owed payments during a retrenchment process. | Is there at least one confidential reporting/grievance channel available for workers? - The assessment found that the factory's written grievance procedures are not implemented adequately: (1) Only one grievance box is available in the factory and the box is placed in a busy area of the sewing department next to the HR office. Workers who file grievances can be easily seen by coworkers or supervisors. (2) The grievance box is not locked. (3) The grievance mechanism and procedure is not posted next to the grievance box. | (1) Ensure the location of grievance boxes is in a private and convenient area for workers to submit grievances and add more boxes so that workers from all departments can have easy access. (2) Ensure the grievance box is locked to prevent unauthorized persons from accessing. (3) Post grievance procedures and mechanisms next to the grievance boxes. |  |  |  | Completed AREAS HAVE LOCKED GRIEVANCE/SUGGESTION BOXES. THIS IS BROUGHT UP DURING ANNUAL ORIENTATION. | Completed
| 9571 | ER.18.1.1-The disciplinary system shall be applied in a fair and nondiscriminatory manner and include a management review of the actions by someone senior to the manager who imposed the disciplinary action. | Are the written workplace rules about discipline fairly applied by the management? - The assessment identified at least one case in which the factory’s written disciplinary procedures were not followed in practice: As per the written notice of decision from the factory's HR department a worker was suspended for 3 days due to absences. There is no record however of a written warning letter being issued before this notice of decision as is called for in the procedures. In addition the disciplinary procedures state that the worker should be given 24 hours to explain his/her absence before a written warning is issued but the notice of decision was issued on the next day after the worker's absence. | In all cases implement a fair disciplinary process that follows the written disciplinary procedures. |  |  |  | Completed | Completed
| 9572 | ER.18.4-The disciplinary system shall include a third party witness during imposition and an appeal process. | Do the disciplinary procedures or existing documents include workers' right to appeal the disciplinary action and workers' ability to have a third party witness during the imposition of disciplinary actions? - The factory's disciplinary procedures do not include workers' right to appeal or to have a 3rd party witness nor are these steps implemented in practice. | Ensure that both disciplinary procedures and implementation include a right to an appeal and to have a third party witness present. |  |  |  | Completed PRODUCTION MANAGER HR AND GRIEVANCE MANAGER OF DEPT ARE ALL PRESENT. | Completed
| 9573 | ER.3.1-Employers shall provide an orientation to new employees at the time of hiring which includes explanations of the employers’ rules compensation package and policies for human resources grievance systems industrial relations including respect of the right to freedom of association workers’ rights and responsibilities FLA Code of Conduct health and safety and environmental protection. | Does the orientation Training to new workers cover all FLA's Code elements and Employment Functions? (Company Code elements are accepted if FLA Codes are fully covered) - Orientation trainings for new workers do not cover all FLA Code elements and Employment Functions. As explained by factory management the orientation for new workers covers only production training. |  |  |  |  | Completed | Completed
| 9574 | ER.6.1-Employers shall have written policies and procedures and implement practices that encourage ongoing training of all categories of workers with the goal of raising or broadening skills in order to advance in their careers within the factory or beyond. | Does the factory have written policies and procedures on personnel development that encourage ongoing training with the goal of raising or broadening workers' skills so they can advance in their careers? - The factory does not have policies and procedures on personnel development. |  |  |  |  | In process. WILL COMPLETE 1/30/25 | In Progress
| 9575 | ER.7.1-Employers shall have written policies and procedures with regard to performance reviews that outline the review steps and process demonstrate linkages to job grading prohibit discrimination are provided in writing and seek feedback and agreement/disagreement from employees in writing and that follow all local legal requirements. | Does the factory have policies and procedures on performance reviews that include steps and processes linkages to job grading nondiscrimination written feedback and compliance with legal requirement? 12300ntestDo workers have access to their evaluations and the right to provide feedback on them? - (1) The factory's policy and procedures for performance reviews do not include a guarantee of non-discrimination or a step to provide workers with written feedback. (2) The factory conducts performance reviews for each worker. However workers are not provided with access to their evaluation records and do not have the right to provide feedback on the results. |  |  |  |  | In Process will complete 1/30/25 | In Progress
| 9576 | FOA.1.1-Employers shall comply with all national laws regulations and procedures concerning freedom of association and collective bargaining. national laws rules and procedures protecting the rights of workers to organize and bargain collectively. Where local laws and FLA standards differ the employer is expected to follow the highest applicable standard. | Does the factory have policies and procedures on freedom of association and collective bargaining? - There are no policies and procedures on freedom of association and collective bargaining. |  |  |  |  | NO UNION IN FACTORY SO THIS IS NOT APPLICABLE. BUT WAGES ARE DISCUSSED DURING ORIENTATION. | Completed
| 9577 | HSE.1-Employers shall comply with all national laws regulations and procedures concerning health safety and the environment. | Has the factory taken proper steps to ensure that workers are not exposed to asbestos? - (1) The factory has not conducted an asbestos risk assessment to ensure the factory has taken proper steps to avoid asbestos exposure. (2) Due to there being no asbestos assessment there is no label for any material in the factory containing asbestos. | (1) Conduct asbestos assessment. (2) Ensure that workers are not exposed to asbestos by labeling all materials containing asbestos if found during the asbestos assessment followed by replacing asbestos materials with other nonhazardous materials. |  |  |  | Completed | Completed
| 9578 | HSE.10.1-Material Safety Data Sheets (MSDS) for all chemicals and hazardous substances used in the workplace must be available at the usage and storage sites of the chemicals and hazardous substances in the local language and the language spoken by workers if different from the local language. | Does the factory have a MSDS or SDS for all chemicals in the factory? - There are no MSDS (Material Safety Data Sheet) available for the fuel or the bleach used in the factory. | Ensure MSDS (Material Safety Data Sheet) are available in the proper languages for all chemicals located in the areas where they are used and stored. |  |  |  | Completed | Completed
| 9579 | HSE.13-All necessary ventilation plumbing electrical noise and lighting services shall be installed and maintained to conform to applicable laws and to prevent or minimize hazardous conditions to workers in the facility. | Is the factory sufficiently illuminated? - The factory's Working Environment Measurements (WEM) indicate failed marks for lighting/illumination. The factory has not taken corrective actions. | Ensure that lighting is adequate for the areas specified by the WEM. |  |  |  | Completed | Completed
| 9580 | HSE.14.1-All production machinery equipment and tools shall be properly guarded and regularly maintained. | Has the factory implemented a complete lockout-tagout maintanence safety system for all relevant equipment? - The factory has not implemented a lockout-tagout program. There are no lockout-tagout devices such as padlocks valve locks cable locks tags etc. available at the factory. There is also no list of equipment and/or machines requiring lockout-tagout. | Implement a lockout-tagout program to ensure safe maintenance. Acquire proper lockout-tagout devices create a list of equipment and/or machines that require lockout-tagout establish written procedures and train relevant workers on the program. |  |  |  | Completed | Completed
| 9581 | HSE.14.2-Workers shall receive training in the proper use and safe operation of machinery equipment and tools they use. | Does the factory provide training to workers operating machinery and vehicles?Does the factory provide safety training to designated workers with special/high-risk responsibilities (working with laser radiation or electrical issues confined space lockout/tagout work at heights)? - (1) There is no training for workers on proper use of machine safety guards. (2) There is no training on work in confined spaces work at heights or lockout/tagout for workers who may have to perform these tasks. (3) The facility currently has two safety officers who are both classified as Safety Officer 2. Given the size of this facility and the risk level local law requires that the facility have one Safety Officer 2 and one Safety Officer 3. | (1) Provide training to workers on machine safety guards. (2) Provide training on confined spaces work at heights and lockout/tagout for relevant workers. (3) Ensure to have one Safety Officer 2 and one Safety Officer 3 employed at the factory. |  |  |  | In progress. WILL COMPLETE 1/30/25 | In Progress
| 9582 | HSE.29-Employers shall provide all necessary protection for workers when working at heights confined spaces and other high-risk areas. | Is fall protection equipment properly used by workers?Is the factory making efforts to protect maintenance workers from the risks related to their jobs including special/dangerous tasks? - (1) There is no body harness available for workers who work at heights. (2) There is no safety rod provided near the factory's electrical panels to push or pull a person that might be electrocuted. | (1) Provide a body harness for workers who work at heights. (2) Provide safety rods at every electrical panel as rescue equipment to push or pull an electrocuted person. |  |  |  | iN PROCESS. wILL COMPLETE 1-30-25 | In Progress
| 9583 | HSE.30.1- Employers shall develop maintain and regularly review health safety and environmental policies to ensure that they comply with all national laws regulations and the FLA Workplace Code concerning health safety and environmental standards regulations and procedures. | Does the factory have policies and procedures regarding environmental protection? Are the health and safety procedures complete (including emergency/evacuation fire safety first aid machine guards PPE etc.? - (1) There are no policies and procedures on environmental protection. (2) The factory's health and safety procedures do not include procedures on lockout-tagout work at heights or work in confined spaces. |  |  |  |  | ANNUAL ORIENTATION IS IN PLACE In process WILL COMPLETE 1-30-25 | In Progress
| 9584 | HSE.6.1-All safety and medical equipment (e.g. fire fighting equipment first aid kits) shall be available in sufficient numbers throughout the workplace maintained and stocked as prescribed and easily accessible to workers. | Does the fire brigade have the appropriate equipment to fight fires (correct PPE breathing apparatus)? - The fire brigade team is not provided with adequate equipment to fight fires such as helmet gloves boots and a self-contained breathing apparatus (SCBA). | Provide fire brigade team with adequate equipment to fight fires such as helmet gloves boots and a self-contained breathing apparatus (SCBA). |  |  |  | Completed File to large to upload | Completed
| 9585 | HSE.7-Workers shall be provided at no cost with all the appropriate and necessary personal protective equipment (e.g. gloves eye protection hearing protection respiratory protection) to effectively prevent unsafe exposure (e.g. inhalation or contact with solvent vapors noise dust) to health and safety hazards including medical waste. | Is PPE provided to the workers and free of charge (gloves eye or hearing protection protective boots Respirators or other respiratory protection)? - (1) There are no safety shoes provided for one mechanic and one maintenance worker. (2) There is no PPE such as eye protection respirator apron or gloves in the maintenance room. | (1) Provide safety shoes for mechanic and maintenance workers. (2) Ensure adequate PPE such as eye protection apron respirator and gloves for maintenance workers. |  |  |  | In practice | Completed
| 9586 | HSE.8-Workers shall be provided with training on the use and maintenance of personal protective equipment. Training shall be upon hire with periodic refresher training offered to all workers. Management will ensure use of PPE as necessary. | Does the factory provide training to all workers regarding PPE usage and maintenance? - There is no training for workers regarding PPE usage and maintenance at the factory. |  |  |  |  | In Process. WILL COMPLETE 1-30-25 | In Progress