## CAP
Repeat | SubformId | Benchmark ID | Benchmark details | Finding details | Recommendation for Immediate Action | Company Plan of Action | Company deadline | Action Taken | Company Progress Status | Repeat
Ongoing
|  |  |  | Member(s) | Fanatics Apparel LLC |  |  |  |  | Option 3
|  |  |  | Country | China |  |  |  |  | Option 4
|  |  |  | Date of Inspection | 2019-07-29 |  |  | VIEW:VW_report_CAPaction for action table | Planned | Option 5
|  |  | ID |  |  |  |  | hiddenfields for import | In Progress
Additional CAP Notes
|  | Benchmark ID and details | Question(s) and findingdetails | Recommendation for Immediate Action | Recommendation for Sustainable Improvement | Company Plan of Action | Company deadline (MM-DD-YYYY) | Action Taken | Company Progress Status
| 15666 | XX.4-Please refer to the assessment report for benchmark information. For assessments conducted prior to 2020 benchmark numbers reflect the FLA’s 2011 Workplace Compliance Benchmarks. | 10 - 1. The factory does not have written job descriptions for any positions. [ER.1.1] 2. The factory does not conduct performance reviews for any workers. [ER.29.1] 3. The factory does not provide workers with written documentation that substantiates all the issues covered in orientation. [ER.15.3] |  |  | 1Factory will set up written job descriptions for all positions 2Factory provide workers with written documentation that substantiates all the issues covered in orientation.3Factory will enhance the procedures on worker's performance reviews and include processes on job rating nondiscrimination and feedback from workers. For sustainable improvement factory will establish policies and procedures integrating workers&rsquo; feedback regarding job description performance grading nondiscrimination and written feedback from workers. Workers will be systematically integrated and consulted in decision-making processes. Related Training and consultation on the above listed topics will be provided to workers.
| 15667 | C.6-All wages including payment for overtime shall be paid directly and in full within legally defined time limits. When no time limits are defined by law compensation shall be paid at least once a month. | 1 - 1. The factory does not contribute to the Housing Provident Fund for any workers. [ER.22.1] 2. The factory does not take workers’ external seniority (previous job experience prior to factory employment) into account when calculating annual leave as required by law. [C.6] 3. The factory does not provide social insurance to all eligible workers. There are total 111 workers working in the factory including 35 recruited after retirement workers. The factory only provided 66 out of 76 (87%) eligible workers with 5 types of social insurances in the latest payment month of July 2019. [C.1] 4. The factory contributes to 5 types of social insurances for 66 out of 76 (87%) eligible workers based on local minimum contribution base of CNY 3368 (USD 478) per month which is lower than legal requirement of worker’s average monthly wage of previous year ranging from CNY 3500 (USD 496) to CNY 4000 (USD 567). [C.10.1] | 1. Provide all workers with legally required Housing Provident Fund. 2. Calculate annual leave based on worker’s cumulative working experience (working age). 3. Provide social insurance to all eligible workers. 4. Contribute to social insurance based on worker’s average monthly wage of previous year. |  | 1. factory will check with the government on the Housing provident fund requirement. 2. factory will consider workers previousl job experience when computing annual leave. 3. Factory will provide training to workers and impove on social insurance coverage.4. Factory will check with government on the use of average monthly wage in computing social insurance contribution. Social Insurance and paid annual leave training will be provided to factory managers. For sustainable improvement: 1) Factory will set up policy and procedures ensuring all employees are paid with at least the legal minimum wage and overtime payment at the legal premium rate. Factory will also keep abreast and update on law regarding any change on legal minimum wage rate2Factory will set up policy and procedure ensuring all legally required paid leave are provided to all workers. Related training will be provided to all workers on legal benefits. 3 Factory will encourage workers to enroll to social insurance scheme and set up plan to increase social insurance coverage. 4Factory will compute social insurance contributions based on the legal requirement. 5Related training on benefit of social insurance wages and employee benefits will be provided to all workers.
| 15668 | XX.1-Please refer to the assessment report for benchmark information. For assessments conducted prior to 2020 benchmark numbers reflect the FLA’s 2011 Workplace Compliance Benchmarks. | 2 - 1. Domestic waste is stored outdoors directly on the ground in an open area near the kitchen instead of being placed in storage containers in the enclosed waste storage area. [HSE.1] 2. The factory has not maintained disposal records for industrial solid waste. [HSE.5.1] 3. The factory does not filer the air emission generated from kitchen before its release into the environment. [HSE.1] 4. The factory has not conducted monitoring on the air emission from kitchen to demonstrate it meets legal standards. [HSE.1] 5. The factory has not conducted an assessment to identify the equipment containing ozone depleting substances (ODSs) e.g. CFCs Halon HCFCs HBFCs Carbon Tetrachloride Methyl Chloroform Methyl Bromides Bromochloromethane or set up plan to phase-out their use. [HSE.1] | 1. Store domestic wastes in storage containers in enclosure area. 2. Maintain disposal records for industrial solid wastes. 3. Filter the air emission generated from kitchen before its release into the environment. 4. Conduct monitoring on the air emission from kitchen annually to demonstrate it meets legal standards. |  | 1. Store domestic wastes in storage containers in enclosed area.2. Maintain disposal records for industrial solid wastes. 3. Fty is consulting with relevant government department regarding air emission from kitchen and an assessment to identify the equipment containing ozone depleting substances. For sustainable improvement: 1. Establish EHS environmental health and safety team. 2. Improve ESH policies and procedures including storing wastes in containers recording waste disposal monitoring on the air emission from kitchen's workers will be systematically integrated and consulted in decision-making processes. Related Training and consultation on the above listed topics will be provided to workers.
| 15669 | HSE.1-Employers shall comply with all national laws regulations and procedures concerning health safety and the environment. | 3 - 1. The electrical scissor operator does not wear metal mesh gloves while working. In addition workers in the sewing workshop do not wear dust-proof masks when handling materials that generate fabric dust. [HSE.8] 2. The factory has not installed needle guards on 10% of the sewing machines or eye protective shields on either of the high speed stitching machines. [HSE.14.1] 3. The factory has not posted safety instructions near most machines including the buttoning machines sewing machines and lamination machines. The factory also has not posted warning signs to remind workers to wear appropriate personal protective equipment (PPE) in the workshops. In addition the warning labels on buttoning machines are in English instead of Chinese. [HSE.14.3] 4. The factory has not installed inner insulation boards on 50% of the electrical panels in production area. Dust and fabric lint have accumulated in the electrical panels in the sewing and packing workshops. Production materials are placed under two electrical panels in sewing and packing workshops. One switch box in the packing workshop and another switch box in the aisle of dormitory building are not covered. [HSE.13] [HSE.25.1] | 1. Strengthen training and supervise workers to use personal protective equipment (PPE) consistently during work hours. 2. Install appropriate machine safety guards and train workers to use safety guards properly during work hours. 3. Post safety instructions on or near machines and post warning signs to remind workers to wear appropriate PPE in workshops. Ensure warning labels on machines are in the language spoken by the workers i.e. Chinese. 4. Install inner insulation boards on all electrical panels clean the electrical panels regularly to ensure they are dust and lint free keep electrical panels free from obstruction and ensure electrical boxes are properly covered. |  | 1The electrical scissor operator wear metal mesh gloves while working. 2 workers in the sewing workshop wear dust-proof masks when handling materials that generate fabric dust. Factory will install needle guards on the sewing machines and eye protective shields on the high speed stitching machines. 3. Factory will post safety instuctions near all machinery. Warning signs will be posted to remind workers of using PPE properly. Also warning labesl will be translated to Chinese. 4. Insulation boards will be installed in all the electrical panels. We will check and clean up all the electrical panels from dust or fabric lint. For sustainable improvement: 1. Strengthen training and supervise workers to use personal protective equipment (PPE) consistently during work hours. (already improved on 2019.10.14) 2. Install appropriate machine safety guards and train workers to use safety guards properly during work hours. (already improved on 2019.10.14) 3. Post safety instructions on or near machines and post warning signs to remind workers to wear appropriate PPE in workshops. Ensure warning labels on machines are in the language spoken by the workers i.e. Chinese. 4. Install inner insulation boards on all electrical panels clean the electrical panels regularly to ensure they are dust and lint free keep electrical panels free from obstruction and ensure electrical boxes are properly covered. (already improved on 2019.10.14)
| 15670 | HSE.1-Employers shall comply with all national laws regulations and procedures concerning health safety and the environment. | 4 - 1. The factory does not clean up the debris in workshops in a timely manner. [HSE.19] 2. The dormitory is not clean or sanitary with lots of dust on the floors of aisles. In addition about 30% of lamps in dormitory aisles are missing bulbs. [HSE.25.1] 3. Kitchen workers do not wear hair nets or hygiene masks while preparing food. [HSE.22.1] 4. One of the two kitchen workers does not have a health certificate. [HSE.22.1] 5. The factory does not keep food samples which is not in compliance with legal requirement of keeping food samples for at least 48 hours in refrigerator. [HSE.19] 6. The factory does not conduct annual drinking water test. The latest testing report was issued in 2017. [HSE.23.1] 7. The factory does not provide soap or drying facilities at the toilets in the production area. [HSE.19] | 1. Keep workshops in good order by cleaning up the debris in a timely manner. 2. Conduct regular cleaning and maintenance in dormitory building. 3. Strengthen training and supervise kitchen workers to wear hair nets and hygiene masks while preparing food. 4. Ensure all kitchen workers obtain health certificates. 5. Keep food samples for at least 48 hours in refrigerator as per legal requirement. 6. Conduct annual drinking water test to ensure it is clean and safe. |  | 1factory cleaned up the debris in workshops in a timely manner. 2. factory cleaned up the dormitory building and added lamps with bulbsin dormitory aisles. 3kitchen workers wear hair nets and hygiene masks while preparing food. 4kitchen worker will apply forthe health certificates.Factory keep food samples for at least 48 hours in refrigerator as per legal requirement. 5Factory provides soap at the toilets in the production area. 6.factory will conduct annualdrinking water test to ensure water is clean and safe. For sustainable improvement 1. Keep workshops in good order by cleaning up the debris in a timely manner.(already improved on 2019.10.14) 2. Conduct regular cleaning and maintenance in dormitory building. (already improved on 2019.10.14) 3. Strengthen training and supervise kitchen workers to wear hair nets and hygiene masks while preparing food. (already improved on 2019.10.14) 4. Ensure all kitchen workers obtain health certificates. (already improved on 2019.10.14) 5. Keep food samples for at least 48 hours in refrigerator as per legal requirement. 6. Conduct annual drinking water test to ensure it is clean and safe. 7Factory provides soap at the toilets in the production area.(already improved on 2019.10.14)
| 15671 | HSE.1-Employers shall comply with all national laws regulations and procedures concerning health safety and the environment. | 5 - 1. The factory does not keep records of work-related injuries including minor injuries and near misses. In addition no records of investigations or corrective actions have been maintained.[HSE.3.2] 2. The factory has not conducted an ergonomic risk assessment or taken proactive steps to reduce repetitive-motion stress or injuries (e.g. breaks adjustable workstations). Workers working in sitting position in the sewing and packing workshops are not provided with adjustable chairs with backrests. [HSE.17.1] 3. The factory has not conducted assessments for determining thermal comfort problem areas. No thermometers are installed to monitor the temperature in the workshops. [HSE.13] 4. The factory was established in 2003 and specializes in garments production with main processes of cutting sewing ironing inspection and packing. However the factory has not conducted any type of occupational health assessment. [HSE.1] 5. The factory has no procedure to manage contractor safety and does not provide safety information to contractors. [HSE.1] |  |  | 1Factory will keep a record for any work-related injuries. 2. Factory will conduct an ergonomic risk assessment and take steps to reduce repetitive motion stress. 3. Factory will use thermometer to measure the comfort level and temperature in the workshop. 4Factory will conduct occupational health assessment. For sustainable improvement: 1The factory is consulting with relative government dept. regarding occupational health assessment 2Establish EHS environmental health and safety team3Improve ESH policies and procedures including keeping a record for any work-related injuries using thermometer to measure the comfort level managing contractor safety.4. Workers will be systematically integrated and consulted in decision-making processes. Related Training and consultation on the above listed topics will be provided to workers.
| 15672 | HSE.1-Employers shall comply with all national laws regulations and procedures concerning health safety and the environment. | 6 - 1. The factory has not contracted a qualified company to conduct annual maintenance for the fire-fighting equipment in both the production area and dormitory area including fire extinguishers fire hydrants smoke detectors and sprinkler system etc. The maintenance labels on fire extinguishers indicate that maintenance was last conducted in 2014 to 2015. [HSE.6.1] [HSE.25.1] 2. The factory has not marked the locations of first aid kits and incorrectly marked the locations of the fire alarms on the evacuation maps in both the production area and dormitory area. In addition about 50% of the evacuation maps in both production area and dormitory area are not consistent with the actual layout. [HSE.5.1] [HSE.25.1] 3. The factory has not conducted assessments after the fire evacuation drills to learn how to improve the evacuation process. [HSE.5.1] | 1. Contract qualified company to conduct annual maintenance of fire-fighting equipment in both production area and dormitory area to ensure they are in good condition and ready to use in case of an emergency. 2. Enhance current evacuation maps in both production area and dormitory area to include complete and accurate information as well as consistent with the actual layout. |  | 1Factory will arrange conduct annual maintenance for the fire-fighting equipment in both the production area and dormitory area including fire extinguishers fire hydrants smoke detectors and sprinkler system. 2. Factory will update the evacuation maps and ensure all the maps are consistent with the actual layout. 3. Factory will conduct assessmetns after the fire drill to impove the evacuation process. For sustainable improvement:1. Contract qualified company to conduct annual maintenance of fire-fighting equipment in both production area and dormitory area to ensure they are in good condition and ready to use in case of an emergency. 2. Enhance current evacuation maps in both production area and dormitory area to include complete and accurate information as well as consistent with the actual layout.
| 15673 | HOW.1.1-Employers shall comply with all national laws regulations and procedures concerning hours of work public holidays and leave. | 7 - 1. The factory did not maintain time records for at least 12 months prior to February 2019. Time records for the period from February 2019 to July 2019 (as of the assessment dates of July 29 and July 30 2019) are maintained and provided for review during the assessment. However time records before February 2019 are not maintained because they were kept in the private computer of social compliance clerk who resigned in February 2019. [ER.23.3] 2. The factory sets the production plan based on 57 hours per week (a total of six days per week with nine point five hours each day including eight regular hours and one point five overtime hours). Factory management sets production targets and production system at a level that workers need to work 17 overtime hours per week. [ER.24] 3. Workers’ monthly overtime hours exceed legal requirement. Time records review for the period from February 2019 to July 2019 notes that the monthly overtime for 90% of workers exceeded 36 hours in all reviewed months except February 2019 with a maximum of 79 overtime hours in March 2019. [HOW.1.1] | 1. Maintain time records for at least 12 months. 2. Ensure overtime hours do not exceed 36 per month. 3. Set production plan based on regular working hours. |  | 1. Factory has updated the computer&rsquo;s system and backed up attendance data to hard disk monthly. 2. Factory will set the production plan based on 40 regular working hours / week. 3. Factory will improve on excessive overtime work to meet the law requirement. For sustainable improvement: 1 Factory will set up policy/procedures in reducing excessive overtime working hours by retaining skillful workers improve workers' satisfaction improve communication between supervisor and workers provide on the job training to improve efficiency.. (will complete on 2020.01.30 ). 2.Factory will eliminate mandatory overtime work requirement on the production plan or require employee to work overtime on a regular basis. The normal working hours will be based on the labor law requirement and communicate to all workers.3Factory will conduct an analysis on overtime work to find out the root cause and to progressively reduce excessive hours of work. (will complete on 2020.01.30 )
| 15674 | XX.2-Please refer to the assessment report for benchmark information. For assessments conducted prior to 2020 benchmark numbers reflect the FLA’s 2011 Workplace Compliance Benchmarks. | 8 - 1. The factory does not provide office space to the trade union. [FOA.15] 2. The factory pays the union dues instead of the workers. [FOA.10] 2. FLA Comments: The Chinese constitution guarantees Freedom of Association; however the Trade Union Act prevents the establishment of trade unions independent of the sole official trade union – the All-China Federation of Trade Unions (ACFTU). According to the International Labor Organization (ILO) many provisions of the Trade Union Act are contrary to the fundamental principles of freedom of association including the non-recognition of the right to strike. As a consequence all factories in China fall short of the ILO standards on the right to organize and bargain collectively. Recently however the government has introduced new regulations that could improve the functioning of the labor relations’ mechanisms. The Amended Trade Union Act of October 2001 stipulates that union committees have to be democratically elected at members’ assemblies and trade unions must be accountable to their members. The trade union has the responsibility to consult with management on key issues of importance to their members and to sign collective agreements. It also grants the trade union an enhanced role in dispute resolution. In December 2003 the Collective Contracts Decree introduced the obligation for representative trade unions and employers to negotiate collective agreements in contrast to the previous system of non-negotiated administrative agreements. [FOA.2] |  |  | Factory will make improvement and ensure freedom of association is exercised fully and legally in the factory according to the law and FLA requirement. Training on freedom of association will be provided to workers.
| 15675 | XX.3-Please refer to the assessment report for benchmark information. For assessments conducted prior to 2020 benchmark numbers reflect the FLA’s 2011 Workplace Compliance Benchmarks. | 9 - 1. The factory has not established policies or procedures on promotion demotion and job reassignment. [ER.30.1] 2. The factory has policies and procedures on hours of work but the procedures do not include the exceptional circumstance such as urgent orders or power outages. [ER.23.1] |  |  | Factory established policies or procedures on promotion demotion and job reassignment immediately. 1Factory established policies or procedures on promotion demotion and job reassignment immediately 2Factory will enhance the procedures on exceptional circumstance such as urgent orders or power outages.3Workers will be systematically integrated and consulted in decision-making processes. 4 Related Training and consultation on the above listed topics will be provided to workers.
| 15676 | XX.5-Please refer to the assessment report for benchmark information. For assessments conducted prior to 2020 benchmark numbers reflect the FLA’s 2011 Workplace Compliance Benchmarks. | 11 - 1. The factory has not conducted a regular review of Employee Handbook and the latest review of Employee Handbook was conducted on November 10 2009. However the factory has conducted management and internal reviews to ensure that other policies and procedures are updated according to local laws FLA Workplace Code and Benchmarks for all Employment Functions. [ER.1.3] 2. The factory does not have qualified staff responsible for social compliance issues at the workplace. Factory management explained that the former staff responsible for social compliance resigned in February 2019 and the factory is still recruiting for the position. [ER.1.2] |  |  | Now we have a full-time staff who is responsible for social compliance issues at the workplace and will conduct a regular review of Employee Handbook. 1Factory will establish policies and procedures regarding establishment implementation and updating of its policies and procedures on Employees' handbookrelated Training will be provided to workers. 2 Factory will conduct management/internal review to ensure policies and procedures are updated according to local laws and the FLA Workplace Code and Benchmarks.3The factory will formally define the person(s) for social compliance issue in the factory or for any employment functions.4Senior management will sign-off on the factory&rsquo;s policies and procedures for implementation. |  | Now we have a full-time staff who is responsible for social compliance issues at the workplace and will conduct a regular review of Employee Handbook. 1Factory will establish policies and procedures regarding establishment implementation and updating of its policies and procedures on Employees' handbookrelated Training will be provided to workers. 2 Factory will conduct management/internal review to ensure policies and procedures are updated according to local laws and the FLA Workplace Code and Benchmarks.3The factory will formally define the person(s) for social compliance issue in the factory or for any employment functions.4Senior management will sign-off on the factory&rsquo;s policies and procedures for implementation.
| 15677 | XX.6-Please refer to the assessment report for benchmark information. For assessments conducted prior to 2020 benchmark numbers reflect the FLA’s 2011 Workplace Compliance Benchmarks. | 12 - 1. The factory does not provide specific training to the relevant supervisors on any of the Employment Functions. [ER.17.1] 2. The factory does not provide training to workers on ergonomics including lifting techniques. [HSE.17.2] 3. The factory does not provide safety training to maintenance workers working with electrical issues and lockout/tagout program. [HSE.14.2] 4. The factory does not provide training to health and safety committee members. [HSE.1] 5. Canteen workers do not receive specific hygiene training. [ER.1.2] 6. Dormitory workers do not receive specific health and safety training. [ER.1.2] |  |  | 1The employment functions training will be provided to relevant supervisors. 2 Ergonomics training will be provided to porter workers. 3Electrical issues and lockout/tagout program training will be provided to maintenance workers. 4Health and safety training will provide to committee members. 5Specific hygiene training will provide to canteen workers. 6Specific health and safety traning will provide to dormitory workers. For sustainable improvement factory will establish policies and procedures integrating workers&rsquo; feedback regarding the employment Functions training ergonomics training electrical issues and lockout/tagout program training health and safety training specific hygiene traning specific health and safety traning establishment implementation and updating of its policies and procedures on Recruitment Hiring Personnel Development; Compensation; Hours of Work; Industrial Relations; Grievance System; Workplace Conduct Discipline; Termination Retrenchment; Environmental Protection; and Health Safety. Workers will be systematically integrated and consulted in decision-making processes. Related Training and consultation on the above listed topics will be provided to workers. |  | 1. The employment functions training will be provided to relevant supervisors. 2 Ergonomics training will be provided to porter workers. 3Electrical issues and lockout/tagout program training will be provided to maintenance workers. 4Health and safety training will provide to committee members. 5Specific hygiene training will provide to canteen workers. 6Specific health and safety traning will provide to dormitory workers.
| 15678 | XX.7-Please refer to the assessment report for benchmark information. For assessments conducted prior to 2020 benchmark numbers reflect the FLA’s 2011 Workplace Compliance Benchmarks. | 13 - 1. The factory does not establish a system to discipline supervisors managers or workers who engage in any form of harassment or abuse. [H/A.11] |  |  | The factory will provided trainings to supervisors on Harassment Abuse and discipling system. For sustainable improvement: factory will establish policies and procedures integrating workers&rsquo; feedback regarding policy and procedures for harassment and Abuse. Workers will be systematically integrated and consulted in decision-making processes. Related Training and consultation on the above listed topics will be provided to workers.