## CAP
Repeat | SubformId | Benchmark ID | Benchmark details | Finding details | Recommendation for Immediate Action | Company Plan of Action | Company deadline | Action Taken | Company Progress Status | Repeat
Ongoing
|  |  |  | Member(s) | New Balance Athletics Inc. |  |  |  |  | Option 3
|  |  |  | Country | Vietnam |  |  |  |  | Option 4
|  |  |  | Date of Inspection | 2022-11-14 |  |  | VIEW:VW_report_CAPaction for action table | Planned | Option 5
|  |  | ID |  |  |  |  | hiddenfields for import | In Progress
|  |  | Additional CAP Notes | New Balance production ended at this factory in February 2026. The decision was due to business reasons. New Balance represented a small percentage of total production at this factory at the time of exit. The exit was not anticipated to have an impact on factory operations. New Balance worked with the factory to ensure non-compliances have been remediated or remediation is in progress.
|  | Benchmark ID and details | Question(s) and findingdetails | Recommendation for Immediate Action | Recommendation for Sustainable Improvement | Company Plan of Action | Company deadline (MM-DD-YYYY) | Action Taken | Company Progress Status
| 11769 | C.1.1-Employers shall comply with all national laws regulations and procedures concerning the payment of compensation to workers. | Applicable to compensation is the factory in compliance with the local legal requirements/ FLA Code in all other areas not previously noted? - The factory has not established a written policy to regularly review and adjust workers' wages. In July 2022 the factory increased the salaries of some workers who had been hired before December 2013 by VND273000/month. For workers with low performance | Develop a policy and procedure for regular wage review including procedures and criteria for performance-based adjustments. Conduct wage adjustments for workers consistently and in line with established policies. |  | - Set up a policy and procedure for regular wage review performance-based adjustments for workers consistently . - Assign a person in charge to follow the issue and compliance. - Monitor periodically to ensure the compliance. | 04-30-2023 | - CSR/ HR is studying and working with management to set up a policy and procedure for regular wage review and performance-based adjustments for workers consistently. - Assigned CSR/ HR in charge to follow the issue and compliance. - CSR/ HR monitor periodically to ensure compliance. | In Progress
| 11770 | C.12.1-All legally mandated deductions for taxes social insurance or other purposes shall be deposited each pay period in the legally defined account or transmitted to the legally defined agency. This includes any lawful garnishments for back taxes etc. | Does the factory use the correct calculation basis for social or medical insurance for all workers? - (1) When a worker takes sick leave or maternity leave for 14 or more days the factory deducts 10.5% of the mandated insurance contribution from his/her pay in that month. For instance one sampled worker took 20 days for maternity leave from March 06 20 | (1) Follow local law by not deducting social insurance unemployment insurance or occupational accident insurance contributions from workers who have 14 maternity or sick leave days in a particular month. (2) Do not deduct insurance contributions from fi |  | Study and update the legal requirements of social insurance. (1) Follow local law by not deducting social insurance unemployment insurance or occupational accident insurance contributions from workers who have 14 maternity or sick leave days in a partic | 02-28-2023 | Personnel studied and updates the legal requirements of social insurance. (1) Follow local law by not deducting social insurance unemployment insurance or occupational accident insurance contributions from workers who have 14 maternity or sick leave days in a particular month. (2) Do not deduct insurance contributions from final payouts when workers leave the factory having 14 or more non-working days in the final month. Similarly do not deduct these contributions for any month when a worker has 14 or more non-working days. (3) (4) Make all required insurance contributions for all workers on time and maintain records in place. Personnel is in charge to comply with the practice. Personnel monitors periodically to ensure compliance. | Completed
| 11771 | C.17-Employers shall ensure that all legally required payroll documents journals and reports are available complete accurate and up-to date. | Does the factory have a payroll and other legally required payment documents? - There are no time records payment records or insurance contribution records for workers employed by onsite contractors including four security guards one gardener and three workers from cleaning services and canteen services. | Monitor and maintain all relevant records of payment and insurance contributions for onsite subcontractors' workers. |  | Study and update the legal requirements for onsite subcontractors' workers. Monitor and maintain all relevant records of payment and insurance contributions for onsite subcontractors' workers. Assign a person in charge to comply the practice. | 10-03-2023 | HR/ OHS is in charge to comply the practice. OHS study and update the legal requirements for onsite subcontractors' workers: four security guards one gardener and three workers from cleaning services and canteen services. Personnel monitors and maintains all relevant records of payment and insurance contributions for onsite subcontractors' workers. | Completed
| 11772 | C.21.1-Employers shall provide all legally mandated benefits including holidays leave bonuses severance payments and 13th month payments to all eligible workers within legally defined time periods. | Does the factory provide workers with all legally mandated fringe benefits such as holidays bonuses or 13th month payments within the legally defined periods?Are termination payouts paid to the workers within the legally required periods? - (1) A workers' final payout is paid on the normal payday of the following month instead of within 14 working days as per legal requirement. (2) Pregnant workers working in hazardous and heavy job positions (such as sewing) are not transferred to light j | (1) Ensure to make final payouts within 14 working days from the resignation day (2) For pregnant workers working in hazardous or heavy job positions ensure to reduce their working hours by 1 hour per day or transfer them to light jobs without decrease i |  | Update the proceed payment working hours and breaks for pregnant workers working in hazardous or heavy job positions (1) Ensure to make final payouts within 14 working days from the resignation day (2) For pregnant workers working in hazardous or heavy | 03-31-2023 | CSR/ HR updates the proceed payment working hours and breaks for pregnant workers working in hazardous or heavy job positions. (1) The factory ensured to make final payouts within 14 working days from the resignation day. HR is responsible to handle this issue. Task done on Nov 2022 (2)The Factory will provide a break for female workers or payback for them as required by local law: Female workers who are working in hazardous or heavy job positions from the time of pregnancy to the end of the period of raising children under 12 months of age if they do not be assigned to less laborious work will be entitled to reduce the working hours by 1 hour per day. In case both two parties agree to work overtime for 1 hour to be shortened they will be paid at the rate of 150% by the employer. Task done on Nov 2022 (3) Updated and waiting to get the approval from Top Management to provide a two-hour break per day as required by local law. - CSR monitors to ensure compliance. | Completed
| 11773 | C.21.2-All benefits shall be calculated correctly | Are all benefits calculated correctly? - Document review found that one worker (out of a sample of 20) who works as a sewing operator only receives 30 sick leave days per year. This was corroborated in sick leave payment records. This worker however should be entitled to at least 40 sick leave | Register all workers who are working in hazardous and heavy job positions as such and ensure that they are entitled to at least 40 sick leave days per year. |  | Double-check with the local authorities to re-register this worker's position accurately as a hazardous job position and provide the corresponding number of sick leave days. Ensure all workers who are working in hazardous and heavy job positions are enti | 03-31-2023 | HR is followup this issue. HR double-checks with the local authorities to re-register this worker's position accurately as a hazardous job position and provide the corresponding number of sick leave days. The factory ensures all workers who are working in hazardous and heavy job positions are entitled to at least 40 sick leave days per year. CSR monitors to ensure compliance. | Completed
| 11774 | C.7-All payments to workers including hourly wages piecework fringe benefits and other incentives shall be calculated recorded and paid accurately. | Does the management calculate salary payments correctly including all hours of work piece work and other incentives? - (1) Per local law workers who are transferred to a new job position with a lower salary are entitled to be paid at their previous salary level for the first 30 working days in the new position. The factory is not in line with this requirement. One sample | For workers are transferred to another position with a lower salary continue to pay the previous salary for 30 working days. |  | Assign a person in charge to follow the issue and compliance. Ensure all workers are transferred to another position with a lower salary and will continue to pay the previous salary for 30 working days. Assign a person to follow up on this issue. Keep mon | 03-31-2023 | HR is in charge to follow the issue and compliance. The Factory ensures all workers are transferred to another position with a lower salary and will be continued to pay the previous salary for 30 working days. | Completed
| 11775 | C.9.3-Employees shall be compensated for overtime hours at such premium rate as is legally required in the producing country | Does the management always pay the correct legally defined premium rates for overtime including for piece rate workers? - The factory does not calculate payment for day and night work on holidays correctly. Time and payment records indicate that on April 10 2022 (a local holiday) the factory applied a holiday night shift rate of an extra 30% from 00:00 to 04:30 and 215% fr | On holidays pay correct overtime rates of 390% for work on the night shift and 300% for work on the day shift following the definitions of night and day shifts established in local law. |  | -Define clearly night and day shifts established in local law. -Pay for the holidays correct overtime rates of 390% for work on the night shift and 300% for work on the day shift. -Assign a person in charge to follow the issue and compliance. -Monitor the | 05-30-2023 | CSR/HR defines clearly night and day shifts established in local law. -The factory is on the way to paying for the holiday's correct overtime rates of 390% for work on the night shift and 300% for work on the day shift (if any). -CSR/HR in charge to follow the issue and compliance. -CSR/HR monitors the actual practice for raising appropriate solutions. | Completed
| 11776 | ER.1.1-Employers shall have in place written policies and practices and maintain proper and accurate records governing all aspects of employment from recruitment hiring and probation including written terms and conditions of employment job descriptions administration of compensation and working hours for all positions through to retrenchment and termination processes. | Does the factory have policies and procedures on nondiscrimination?Does the factory have policies and procedures on forced labor?Does the factory have policies and procedures on child labor?Is there a written job description prepared for all positions when personnel need to be hired? - (1) The factory's procedure for non-discrimination was established on March 01 2021. This document is missing key elements forbidding discrimination along sexual orientation nationality race marital status disability HIV/AIDS status pregnancy age |  |  | (1)Study and update the factory's procedure for non-discrimination. (2) Developed a procedure to handle cases of forced labor in the factory including the steps to discipline those responsible for violations. (3) Developed a procedure to handle cases of | 04-30-2023 | CSR/ OHS is in charge to follow the issue. (1)CSR studies and update the factory's procedure for non-discrimination. (2) CSR developed a procedure to handle cases of forced labor in the factory including the steps to discipline those responsible for violations. (3)CSR developed a procedure to handle cases of child labor in the factory including the steps to discipline those responsible for child labor violations. (4)HR dept updates and set up job descriptions by written document for all jobs/positions in the factory. CSR monitors the actual practice to ensure compliance. | In Progress
| 11777 | ER.1.2-Employers shall assign responsibility for the administration of human resources to a clearly defined and adequately qualified staff member or staff members and ensure workers at all levels receive communication and training about existing policies and procedures or any revisions. | Does the factory provide any ongoing training to workers on all FLA's Code elements and Employment Functions?Does the factory have a clearly defined qualified staff responsible of social compliance issues at the workplace? - (1) The ongoing training conducted for workers does not cover the FLA Code elements of Employment Relationship Nondiscrimination Harassment or Abuse Forced Labor Child Labor Freedom of Association and Collective Bargaining Hours of work or Compensa |  |  | Study the FLA Code (1) Conduct training for workers are cover the FLA Code elements of Employment Relationship Nondiscrimination Harassment or Abuse Forced Labor Child Labor Freedom of Association and Collective Bargaining Hours of work or Compen | 06-30-2023 | CSR/ OHS/ HR are studying the FLA Code (1) CSR/ HR conduct training for workers are cover the FLA Code elements of Employment Relationship Nondiscrimination Harassment or Abuse Forced Labor Child Labor Freedom of Association and Collective Bargaining Hours of work or Compensation. (2) Factory defines clearly the CSR/ HR/ OHS responsible for each FLA�s Code elements and Employment Functions. . | In Progress
| 11778 | ER.1.3-Employers should implement an annual review process with input from workers of all policies procedures and their implementation to ensure they meet legal requirements and the FLA Workplace Code. | Are the factory's policies and procedures on all FLA's Code elements and Employment Functions regularly reviewed?Are workers consulted or integrated in the decision-making process of aspects concerning workplace and working conditions (e.g. creation or revision of policies and procedures changes on production processes hours of work etc.)? - (1) There are no records or data in place to verify that the factory conducts a regular comprehensive review of policies and procedures. (2) Workers are not consulted or integrated into the decision-making process for decisions concerning their workplac |  |  | Assign person in charge to follow the issue. (1) The factory conducts a regular comprehensive review of policies and procedures and keeps records. (2) Workers are consulted or integrated into the decision-making process for decisions concerning their | 04-30-2023 | CSR/ OHS is in charge to follow the issue. (1) The factory conducts a regular comprehensive review of policies and procedures and keeps records. (2) Workers are consulted or integrated into the decision-making process for decisions concerning their work and working conditions before the policies and procedures are established by the social compliance HR and HSE departments. | In Progress
| 11779 | ER.15.3-Employers shall not demand that workers sign any declaration of good health waivers or releases of other rights as a condition of receiving severance pay or other legal benefits* from the company and shall not threaten to withhold benefits if workers do not sign. | Do workers receive severance pay and other legal termination benefits without signing a declaration of good health waiver or other release of rights? - (1) The factory did not include the one-month probation period when calculating and paying severance allowances for workers who resigned before February 2022. The factory fixed this calculation error from February 2022 onwards but has not paid back the w | (1) Pay the correct severance allowance for resigned workers as per local law. (2) Pay holidays for all workers who are under employment contracts with the factory. |  | Assign a person in charge to follow the issue and compliance. 1) Proces pay the correct severance allowance for resigned workers as per local law. (2) Proces Pay holidays for all workers who are under employment contracts with the factory. | 03-31-2023 | HR is in charge to follow the issue and compliance. 1) Proces payment the severance allowance for resigned workers as per local law. (2) Proces pyment the holidays for all workers who are under employment contracts with the factory. CSR monitors periodically to ensure compliance. | Completed
| 11780 | ER.17.1-Employers shall have a clear and transparent system of worker and management communication that enables workers to consult with and provide input to management. This might include suggestion boxes worker committees designated spaces for worker meetings union representatives and meetings between management and workers’ representatives. | Does the factory have a policies and procedures on grievance system?Do the factories policies and procedures regarding the Grievance System meet all requirements outlined in local law and the FLA Code of Conduct? - Although the factory has suggestion boxes for workers to lodge grievances or other issues there is no policy or procedure to ensure workers' confidentiality. |  |  | Assign a person in charge to follow the issue Set up the policy or procedure to ensure the factory's confidentiality suggestion boxes. Regularly monitor and evaluate for necessary adjustment and ensure the compliance. | 03-31-2023 | HR is in charge to follow the issue. HR set up the policy or procedure to ensure the factory's confidentiality suggestion boxes. CSR/HR dept regularly monitor and evaluate for necessary adjustment and ensure the compliance. | In Progress
| 11781 | ER.19.1-Employers shall maintain on file all documentation needed to demonstrate compliance with the FLA Workplace Code and required laws. | Do employment terms and conditions align with national laws freely negotiated CBA and FLA Code? - (1) One sampled sewing worker remained in the probation period for 31 days (March 01 2022 to March 31) instead of the stipulated 30 days. (2) Labor contracts at the factory are not updated with the employer's and worker's email address and phone number | (1) Follow local law by setting probation time for all positions to 6 working days 30 days or 60 days and linking probation time with the job position and job functions. (2) Include the employer's and worker's email address and phone number if any in |  | Study and update the legal requirements Train the person in charge (1) Follow local law by setting probation time for all positions to 6 working days 30 days or 60 days and linking probation time with the job position and job functions. (2) Include the | 03-31-2023 | HR dept study and update the legal requirements. HR leader trains the person in charge and new HR staff. (1) The factory follows local law by setting probation time for all positions to 6 working days 30 days or 60 days and linking probation time with the job position and job functions. (2) HR included the worker's email address and phone number in labor contracts. For the addition of the employer's email address and phone number in the employment contract the HR dept is waiting for approval from the General Director due to the current situation of anonymous messages and letters threatening to threaten and disturbing via email and cell phone number. | Completed
| 11782 | ER.3.1-Employers shall provide an orientation to new employees at the time of hiring which includes explanations of the employers’ rules compensation package and policies for human resources grievance systems industrial relations including respect of the right to freedom of association workers’ rights and responsibilities FLA Code of Conduct health and safety and environmental protection. | Does the orientation Training to new workers cover all FLA's Code elements and Employment Functions? (Company Code elements are accepted if FLA Codes are fully covered) - Between November 2021 and the date of the assessment the factory did not conduct full orientation training on the FLA Code elements. Orientation trainings only covered general information about health & safety working hours and payment. Factory managem |  |  | Study the FLA Code Conduct training for workers are cover the FLA Code elements Define clearly the qualified staff responsible for training Assign a person in charge to follow the issue. Monitor the actual practice to ensure compliance. | 05-30-2023 | CSR/ OHS/ HR are studying the FLA Code CSR/ HR conduct training for workers are cover the FLA Code elements of Employment Relationship Nondiscrimination Harassment or Abuse Forced Labor Child Labor Freedom of Association and Collective Bargaining Hours of work or Compensation. Factory defines clearly the CSR/ HR/ OHS responsible for each FLA�s Code elements and Employment Functions. | Completed
| 11783 | ER.4-Employers shall inform workers about workplace rules environmental protection systems health and safety information and laws regarding workers’ rights with respect to freedom of association compensation working hours and any other legally required information and the FLA Code through appropriate means including posted in local language(s) throughout the workplace’s common areas. | Is the FLA Code made available/communicated to the workers? - There is no mechanism to ensure that workers receive regular communication on the FLA Code. |  |  | Study and update the FLA Code Set up a mechanism to ensure that workers receive regular communication on the FLA Code. Assign a person in charge to follow the issue. Monitor the actual practice to ensure compliance. | 05-30-2023 | CSR/ HR study and update the FLA Code HR set up a mechanism to ensure that workers receive regular communication on the FLA Code. | Planned
| 11784 | ER.5.1-Employers shall ensure that all supervisors are trained in national laws workplace regulations and the FLA Code workplace grievance systems and the appropriate practices to ensure compliance. | Does the factory provide any specific training to the relevant supervisors that includes all FLA's Code elements and Employment Functions? - The factory has not conducted training for supervisors on the FLA Code in the last 12 months. |  |  | Study the FLA Code Conduct training for supervisor on the FLA Code elements. Define clearly the qualified staff responsible for training Assign a person in charge to follow the issue. Monitor the actual practice to ensure compliance. | 05-30-2023 | CSR/ HR are studying the FLA Code CSR/ HR conduct training for supervisors on the FLA Code. | Completed
| 11785 | ER.6.1-Employers shall have written policies and procedures and implement practices that encourage ongoing training of all categories of workers with the goal of raising or broadening skills in order to advance in their careers within the factory or beyond. | Does the factory have written policies and procedures on personnel development that encourage ongoing training with the goal of raising or broadening workers' skills so they can advance in their careers? - The factory has not developed written policies and procedures on personnel development that encourage ongoing training with the goal of raising or broadening workers' skills so they can advance in their careers. |  |  | Study to developed written policies and procedures on personnel development that encourage ongoing training with the goal of raising or broadening workers' skills so they can advance in their careers. Assign a person responsible for this. Regularly monito | 04-30-2023 | CSR/HR is responsible for this. HR studies to develop written policies and procedures on personnel development that encourage ongoing training with the goal of raising or broadening workers' skills so they can advance in their careers. | In Progress
| 11786 | ER.7.1-Employers shall have written policies and procedures with regard to performance reviews that outline the review steps and process demonstrate linkages to job grading prohibit discrimination are provided in writing and seek feedback and agreement/disagreement from employees in writing and that follow all local legal requirements. | Does the factory have policies and procedures on performance reviews that include steps and processes linkages to job grading nondiscrimination written feedback and compliance with legal requirement? 12300ntestDoes the review and evaluation process assess performance objectively? - The factory has not developed policies or procedures on performance reviews that include steps and processes linkages to job grading nondiscrimination written feedback and compliance with the legal requirement. |  |  | Study to developed policies or procedures on performance reviews that include steps and processes linkages to job grading nondiscrimination written feedback and compliance with the legal requirement. Assign a person responsible for this. Regularly mon | 04-30-2023 | CSR/HR is responsible for this. HR studies to develop procedures on performance reviews that include steps and processes linkages to job grading nondiscrimination written feedback and compliance with the legal requirement. | In Progress
| 11787 | ER.8-Employers shall have written policies and procedures with regard to promotion demotion and job reassignment that outline the criteria demonstrate linkages to job grading and prohibit discrimination or use of demotion or job reassignment as a form of penalty or punishment are provided in writing and seek feedback from employees in writing and follow all local legal requirements. | Does the factory have policies and procedures on promotion demotion and job reassignment? - The factory has not developed policies or procedures for promotion and demotion. Factory management explained that promotion is based on the results of performance evaluations. The evaluation forms are filled out by department managers the general manage |  |  | Study to develop policies or procedures for promotion and demotion. Assign a person responsible for this. Works with top management to raise clearly performance evaluations forms Regularly monitor and evaluate for necessary adjustments and ensure complian | 05-30-2023 | CSR/ HR is responsible for this. HR studies to develop procedures for promotion and demotion. CSR/ HR works with top management to raise the performance evaluations forms and items clearly | In Progress
| 11788 | FOA.1.1-Employers shall comply with all national laws regulations and procedures concerning freedom of association and collective bargaining. national laws rules and procedures protecting the rights of workers to organize and bargain collectively. Where local laws and FLA standards differ the employer is expected to follow the highest applicable standard. | Applicable to freedom of association collective bargain or strike is the factory in compliance with the local legal requirements/ FLA Code in all other areas not previously noted? - FLA Comment: Vietnam has not ratified ILO Convention 87. Under Vietnamese law all unions are required to affiliate with a single trade union the Vietnam General Confederation of Labor (VGCL) which is affiliated with the Communist Party. With respect to such union monopolies the ILO Committee on Freedom of Association has stated that “the rights of workers to establish organizations of their own choosing implies… the effective possibility of forming… [trade unions] independent both of those which exist already and of any political party.” Vietnam’s legal framework is therefore not compatible with the ILO Principles on Freedom of Association and as such all factories in Vietnam fail to comply with the FLA Code standard on Freedom of Association. |  |  |  | 01-01-1900 |  | Planned
| 11789 | FOA.7-Employers shall comply with all relevant provisions where national laws provide special protection to workers or worker representatives engaged in a particular union activity (such as union formation) or to worker representatives with a particular status (such as founding union members or current union office holders). | Does management comply with all relevant provisions where national laws provide special protection to worker representatives engaged in a particular union activity (such as founding members)? - (1) The factory's regulations have not been updated to reflect new local laws on overtime holidays benefits for female workers re-assignment of employees against his/her employment contract cases in which reassignment of employees are permitted and a | (1) Update the factory’s internal regulations according to the new labor laws. (2) Update the factory's CBA to reflect new labor laws. |  | (1) Update the factory�s internal regulations according to the new labor laws. -Review and complete the policy and procedure on labor discipline in place for implement as being required by local law. -Announce to all workers about these. -Define clearly t | 05-30-2023 | HR is in charge to follow the issue and compliance. (1) CSR/HR updates the factory�s internal regulations according to the new labor laws. -CSR/HR reviews and complete the policy and procedure on labor discipline in place for implement as being required by local law. -HR announces to all I47workers about these. -CSR defines clearly the key contents of cases in which reassignment of employees are permitted actions against sexual harassment in the workplace. (2) CSR and Trade Union update the factory's CBA to reflect new labor laws. - Complete the revised internal rule and the factory's CBA to re-register to get their approval on Apr 2023. | In Progress
| 11790 | H/A.8.3-Employers shall develop implement and monitor policy and procedures for eliminating the risk of violence harassment and abuse in the workplace. Policies and procedures shall include a clear statement that violence harassment and abuse will not be tolerated procedures for the investigation of allegations and measures to protect any complainants victims and witnesses. | Does the factory have a written policy on harassment or abuse including a system to discipline supervisors managers and workers who engage in any form of harassment or abuse? - There is no specific policy and procedure to discipline supervisors managers and workers who commit acts of harassment and abuse. |  |  | -Update and study the legal requirements - Set up the specific policy and procedure to discipline supervisors managers and workers who commit acts of harassment and abuse. - Assign a person in charge to comply the practice. - Monitor periodically to ens | 03-31-2023 | - HR dept is in charge to comply the practice. -HR updates and studies the legal requirements. - HR set up the specific policy and procedure to discipline supervisors managers and workers who commit acts of harassment and abuse. -CSR/ HR monitor periodically to ensure the complaince. | In Progress
| 11791 | HSE.1-Employers shall comply with all national laws regulations and procedures concerning health safety and the environment. | Applicable to Health Safety and Environment is the factory in compliance with the local legal requirements/ FLA Code in all other areas not previously noted?Has the factory taken proper steps to ensure that workers are not exposed to asbestos? - (1) The factory provided two periodic health checks in 2021 but there was no occupational health check conducted for workers working heavy and hazardous jobs (such as stitching cutting and screen-printing) as required by law. (2) The factory does not | Provide an occupational health check at least twice a year for all workers working in heavy and hazardous jobs. |  | (1)-implement according the law requests. -List out workers and dept to be examined for an occupational health check. -Get approval from the top management - Assign a person responsible for this issue. (2)-Study the legal requirements asbestos contaminate | 06-30-2023 | (1)-Waiting to get approval from the top management. -Listed out workers and dept to be examined for an occupational health check. - Assigned OSH responsible for this issue. (2) - Assigned OSH is in charge and responsible for this issue. - OSH officer studies the legal requirements asbestos contaminated materials and then writes procedure. -Scheduled to be completed on 4/15 | Completed
| 11792 | HSE.13-All necessary ventilation plumbing electrical noise and lighting services shall be installed and maintained to conform to applicable laws and to prevent or minimize hazardous conditions to workers in the facility. | Has management conducted any assessments for determining thermal comfort problem areas?Does factory ensure that electrical panels fans machines headlamps etc. are dust and lint free?Are electrical problems timely and adequately fixed? - (1) There is no heat stress management procedure at the factory. The factory has not conducted a heat stress assessment for areas processes and operations with potential heat problems such as the air compressor house heat pressing processes and outdoo | (1) Establish a heat stress management procedure and conduct heat stress assessments for relevant areas processes and operations. (2) Install inner safety covers for all electrical panels in the factory. (3) Conduct regular inspections of the electrical |  | (1) -Study the legal requirements -Define who is in charge of responding to the process. -Establish a heat stress management procedure and conduct heat stress assessments for relevant areas processes and operations. (2) -Install inner safety covers for | 04-30-2023 | (1) -Defined OSH is in charge of responding to the process. -OSH officer is studying the legal requirements - HR updates and establishes a heat stress management procedure and conducts heat stress assessments for relevant areas processes and operations. (2) - Assigned electrician responsible for this issue. -The electrician installs inner safety covers for all electrical panels in the factory. - CSR/ OSH officer monitors and regular checks to ensure improvement. (3) - Assigned an electrician responsible to be in charge. - The electrician conducts regular inspections of the electrical system and maintains inspection records. - HR is responsible to be in charge of checking and monitoring | Completed
| 11793 | HSE.14.1-All production machinery equipment and tools shall be properly guarded and regularly maintained. | Are traffic lanes and walk paths clearly marked?Are all machines properly guarded as required?Are compressed gas cylinders used stored and transported properly? Has the factory implemented a complete lockout-tagout maintanence safety system for all relevant equipment? - (1) There are no markings for vehicle traffic lanes and pedestrian walk paths in the factory compound. In addition there are no warning signs for forklift hazards and no designated forklift routes at the materials warehouse and finished goods warehouse. | (1) Mark traffic lanes and walk paths post forklift warning sign and mark forklift traveling routes at the materials warehouse and finished goods warehouse. (2) Install safety mechanisms for eyelet snapping machines install needle guards for stitching |  | (1)-Mark traffic lanes and walk paths post forklift warning signs and mark forklift traveling routes at the materials warehouse and finished goods warehouse. -Define who is in charge of responding to the process. (2) -Install safety mechanisms for eyelet | 04-30-2023 | (1)-OSH officer is in charge of processing. - OSH officer is studying how to mark traffic lanes and walk paths post forklift warning signs and mark forklift traveling routes at the materials warehouse and finished goods warehouse to improve. (2) -Mechanic staff is in charge of installing. -Install safety mechanisms for eyelet snapping machines and install needle guards for stitching machines to ensure all are in safe manners. -OSH officer works with the maintenance dept to install additional. -Working with the catering service to install safety fences for the LPG storage area. - Assign a person in charge to follow the issue and compliance. (3) -Working with the catering service to install the additional proper equipment. -The catering service is in charge to install proper equipment to transport compressed gas cylinders from the ground floor to the kitchen (upper floor) and installing LPG detectors at the LPG properly. (4) -OSH officer refers to the law request in detail. -Setting up to purchase proper LOTO devices. - The maintenance/mechanic staff obtains and uses proper LOTO devices for all relevant equipment and machinery. - The maintenance/mechanic staff who is in charge of responsible. | Completed
| 11794 | HSE.14.2-Workers shall receive training in the proper use and safe operation of machinery equipment and tools they use. | Does the factory provide safety training to designated workers with special/high-risk responsibilities (working with laser radiation or electrical issues confined space lockout/tagout work at heights)? - (1) The factory's electricians do not have vocational degrees or occupational health and safety training certificates. (2) Workers in job positions requiring occupational health and safety (OHS) training certificates (those working with lasers electrical | Provide training on vocational degrees and occupational health and safety certification to all workers whose roles require them. |  | - Assign a person in charge this issue. -Provide training on vocational degrees and occupational health and safety certification to all workers whose roles require them. -Keep monitor the practise closely. | 05-30-2023 | OSH is in charge to conduct to provide training on vocational degrees and occupational health and safety certification to all workers whose roles require them. -CSR/ OSH keeps monitoring the practice closely. | Completed
| 11795 | HSE.14.3-Employers shall ensure safety instructions are either displayed or posted near all machinery or are readily accessible to the workers in language(s) spoken by workers. | Do lasers have the appropriate signs?Are safety instructions displayed or posted near machinery in workers' language(s)? - (1) There is no warning sign operating procedure or safety instruction posted at the laser cutting machine in the production workshop. (2) The factory has posted warning signs but there is no operating procedure or safety instruction posted for any of | (1) Post hazard signs operating procedures and safety instructions for the laser cutting machine in the workforce's language/s. (2) Post warning signs operating procedures and safety instruction for all machines and electric forklifts in the workforce |  | (1)- Assign a clear responsible person to be in charge. - Post hazard signs operating procedures and safety instructions for the laser cutting machine in the workforce's language/s. - Train workers for their well understanding of all warning signs oper | 04-30-2023 | (1)- Assigned OSH responsible to be in charge. - OSH posts hazard signs operating procedures and safety instructions for the laser cutting machine in the workforce's language/s. - OSH updates and trains workers for their well understanding of all warning signs operating procedures or safety instructions posted. (2)-Assigned OSH officer/ mechanic staff are responsible to be in charge of checking and monitoring the safety of equipment then raise appropriate solutions for improvement. - OSH updates and posts warning signs operating procedures and safety instructions for all machines and electric forklifts in the workforce's language/s. -OSH keeps monitoring the safety of the equipment. | Completed
| 11796 | HSE.17.1-Workstations including seating and standing arrangements and reach required to obtain tools shall be designed and set-up in such a manner as to minimize bodily strains. | Is the factory taking proactive steps to reduce repetitive-motion stress or injuries (breaks adjustable workstations)? - The factory does not take proactive steps to reduce repetitive-motion stress or injuries such as installing adjustable workstations. In particular the factory does not provide chairs with backrests for jobs performed sitting down. | Provide chairs with backrests for workers who work sitting down. |  | -Study the legal requirements -Define who is in charge of responding to the process. -Get approval from the top management -Provide chairs with backrests for workers who work sitting down. | 05-30-2023 | -Waiting to get approval from the top management. -Mechenic staff is in charge of installing -OSH staff is responsible for checking closely. | Planned
| 11797 | HSE.18.2-Medical staff shall be fully licensed and recognized under applicable national rules and regulations. | Is the staff at medical facilities qualified/licensed? - There is no occupational health certificate or safety training certificate on file for the medical staffer working at the factory. | Provide certification training on occupational health and safety to the medical staff. |  | - Medical staff must be trained as group 5 -Provide certification training on occupational health and safety to the medical staff. - Assign a person in charge to follow the compliance. | 11-30-2022 | -The factory has conducted certification training on occupational health and safety for the medical staff. -The task is done on Nov 2022 | Completed
| 11798 | HSE.18.3.1-Medicines of which the expiration date has passed must be replaced immediately and disposed of in a safe manner. | Are all the medicine in use and in supply within the expiration date? - The factory does not conduct checks to ensure that all first aid items supplied and used at the factory are within their expiration date. | Conduct regular checks for all first aid items to ensure that they are fully stocked and not expired. |  | - Re- checked all first aid items -Conduct regular checks for all first aid items to ensure that they are fully stocked and not expired - Assign a person in charge to follow the issue and compliance. | 03-31-2023 | - Assigned OSH in charge to follow the issue and compliance. - OSH officer is re- checked all first aid items and then referred to the law requests in detail. -OSH officer conducts regular checks for all first aid items to ensure that they are fully stocked and not expired. | Completed
| 11799 | HSE.19-All facilities including workplace buildings toilets canteens kitchens and clinics shall be kept clean and safe and be in compliance with all applicable laws including relevant sanitation medical and safety and health regulations. | Does the factory provide adequate soap and drying facilities in the bathroom? - There is no soap hand sanitizer toilet tissues or drying facilities in the toilet areas. | Provide soap and a way to dry one's hands in the toilet areas. |  | -Implement according the law requests. -Provide soap and a way to dry one's hands in the toilet areas. - Assign a person in charge to comply the practice. - Monitor periodically to ensure the complaince. | 03-31-2023 | Listed out and study a way to dry one's hands in the toilet areas. Provided soap in the toilet areas Assigned OSH responsible for this issue and monitor periodically to ensure the complaince | In Progress
| 11800 | HSE.28-Employers shall create a system to ensure that all necessary Health and Safety protections are provided for external contractors; including protection when working within confined spaces maintenance issues and general Health and Safety Issues. | Does the factory provides safety information to contractors? - There is no contractor safety management procedure in place. The factory does not provide safety information conduct safety inspections or issue work permits for onsite contractors. |  |  | - Set up the contractor safety management procedure. - Assign a person responsible for this issue. | 03-31-2023 | Assigned OSH in charge to follow the issue and compliance. OSH is studying to set up the contractor safety management procedure. | Completed
| 11801 | HSE.29-Employers shall provide all necessary protection for workers when working at heights confined spaces and other high-risk areas. | Does each confined space have appropriate protections to ensure that there is no unauthorized entry including signs?Is the procedure for entering confined spaces safely followed (safe atmosphere rescue equipment ready to usetrained observer present)?Do high work areas (higher than 18 meter) have fall protection (walls fences or other barriers) and are they paroperly marked? - (1) There is no warning sign no sign restricting access and no lock to prevent unauthorized entry to confined spaces (water tanks sewers). (2) There is no safe operating procedure for working in confined spaces safely by ensuring safe atmosphere havin | (1) Install warning signs ""no unauthorized access"" signs and locks to prevent unauthorized entry to confined spaces. (2) Establish safe operating procedures for working in confined spaces. (3) Install warning signs ""no unauthorized access"" signs and f |  | (1) -Install warning signs ""no unauthorized access"" signs and locks to prevent unauthorized entry to confined spaces. -Assign a person in charge to follow the compliance. -Keep regular monitors. (2) -Establish safe operating procedures for working in co | 03-31-2023 | (1) -Assigned OSH officer in charge to follow the compliance. -Install warning signs ""no unauthorized access"" signs and locks to prevent unauthorized entry to confined spaces. - OSH is regularly monitors. (2)-OSH studying to establish safe operating procedures for working in confined spaces. - OSH is responsible for this and regularly monitors and evaluates. (3) OSH studying to install warning signs ""no unauthorized access"" signs and fall protection (walls fences or other barriers) for all high platforms. - OSH works with mechanic staff to install wheel locks for the moving stairs and conduct regular inspections. | Completed
| 11802 | HSE.30.1-Employers shall develop maintain and regularly review health safety and environmental policies to ensure that they comply with all national laws regulations and the FLA Workplace Code concerning health safety and environmental standards regulations and procedures. | Does the factory have policies and procedures regarding environmental protection? - There are no procedures on air emissions in place only a chemical emergency response procedure. |  |  | - Study the legal requirements - Set up a policy and procedure for air emissions in the workshop. - Assign a person in charge to follow the issue and compliance. - Monitor periodically to ensure compliance. | 03-30-2023 | OSH staff is in charge to follow the issue and compliance. - OSH studies the legal requirements and then set up a policy and procedure for air emissions in the workshop. -OSH monitors periodically to ensure compliance. | Completed
| 11803 | HSE.30.2.6-The health safety and environmental policies shall contain the framework for a comprehensive health safety and environmental management system including a HS&E risk assessment within which the following are clear and regularly tested and reviewed:protections to workers who allege health safety and environmental violations; | Has the factory conducted a risk assessment? - The OHS (occupational health and safety) risk assessment does not cover laser hazards for the laser cutting machine or confined space hazards. No risk assessment has been conducted for transmittable diseases (bloodborne pathogens) in the factory. In addit | Conduct risk assessments for laser hazards confined space hazards and transmittable diseases. Update the OHS risk assessment at least once a year as required by law. |  | - Update and study the legal requirements. -Conduct risk assessments for laser hazards confined space hazards and transmittable diseases. -Update the OHS risk assessment at least once a year as required by law. - Assign a person in charge this issue to | 03-31-2023 | OHS update and study the legal requirements. -OSH conducts risk assessments for laser hazards confined space hazards and transmittable diseases. -Ms. Hanh updates the OHS risk assessment at least once a year as required by law. - Ms. Chi is following up this issue. | Completed
| 11804 | HSE.4.1-Employers shall at all times be in possession of all legally required and valid permits and certificates related to health safety and environmental issues such as: Purchase and storage of chemicals; Fire safety inspections; Machinery inspections; Waste disposal; Environmental licenses/permits;Sanitation permits including those required for canteens; and Vehicle inspection and driver permits for all employer provided transportation. | Does the factory have all legally required permits and certificates related to health safety and environment aspects? - There is no safety inspection certificate for one observed pressure vessel (200 liters working pressure 10 bars) at the fire pump station. | Conduct periodic safety inspections and maintain inspection certificates for all machines and equipment where required including pressurized vessels. |  | - Update and study the legal requirement. -Conduct periodic safety inspections and maintain inspection certificates for pressurized vessels. - Assign a person in charge to follow the compliance | 04-30-2023 | OSH update and study the legal requirement. -OSH conducts periodic safety inspections and maintains inspection certificates for pressurized vessels. - OHS officer is in charge to follow the compliance | Completed
| 11805 | HSE.5.1-All applicable legally required or recommended elements of safe evacuation shall be complied with including all of the following elements: posting evacuation plans; the installation and maintenance of fire alarms; the installation and maintenance of emergency lighting; ensuring aisles/exits are not blocked and that workers are not blocked within their workstations; employee education and training; and evacuation procedures and fire drills. | Are emergency exits clearly marked?Do all emergency exits open in the direction of evacuation?Are there clear and easily identifiable marking on the floor wall or otherwise indicating exit routes for each work area? - (1) The finished goods warehouse which is about 840 square meters with two workers usually working inside does not have an exit sign posted. (2) One out of two emergency exit doors at the materials warehouse and one emergency exit door at the finished g | (1) Install illuminated exit signs at the finished goods warehouse. (2) Ensure all emergency exits open in the direction of evacuation. (3) Post evacuation maps at the motorbike parking lot and canteen. |  | - Assign a person in charge to follow the issue and compliance. -Install illuminated exit signs at the finished goods warehouse. - Ensure all emergency exits open in the direction of evacuation. -Post evacuation maps at the motorbike parking lot and cante | 05-30-2023 | OSH is in charge to follow the issue and compliance. - OSH works with maintenance to install illuminated exit signs at the finished goods warehouse. -The electrician staff removed two exit signs on 02 rolling doors at the material warehouse as it has an emergency exit door with an outward-opening door. -Waiting to get approval from the top management to replace the rolling door at the finished goods warehouse with an outward-opening door. -Ensure all emergency exits open in the direction of evacuation. -The Captain of the Firefighting team is in charge to post evacuation maps at the motorbike parking lot and canteen. - OSH monitors periodically to ensure compliance. | Completed
| 11806 | HSE.5.1.4-All applicable legally required or recommended elements of safe evacuation shall be complied with including all the following: ensuring aisles/exits are not blocked and that workers are not blocked within their workstations | Are emergency exits free from obstruction? - The assessment observed that one out of three exit routes at the materials warehouse and two out of six exit routes at the production workshop were partially obstructed by materials and products. | Ensure all exit routes are free from obstruction at all times. |  | - Check the available status of the escape route periodically to ensure all exit routes are free from obstruction at all times. -Train workers about the importance of escape route availability in emergency case. - Assign a person in charge to check and r | 03-15-2023 | OSH collaborator members to check the availability status of the escape route periodically to ensure all exit routes are free from obstruction at all times. OSH trains all team leaders and workers about the importance of escape route availability in emergency cases. - OSH officer and OSH collaborator members are in charge to check and remind team leaders. - OSH regularly checks and monitors and raise solution for necessary adjustment. | Completed
| 11807 | HSE.6.1-All safety and medical equipment (e.g. fire fighting equipment first aid kits) shall be available in sufficient numbers throughout the workplace maintained and stocked as prescribed and easily accessible to workers. | Are there functioning eyewash facilities and showers where needed? - The factory has eyewash devices but does not have emergency showers at the chemical storage warehouse or the screen-printing workshops. | Install emergency showers at the chemical storage warehouse and screen-printing workshop. |  | - list out the kind ofemergency showers then study the convenient way to install. - The admin contact with supplier to provide proper equipment. - Ensure it in safe manners -Assign a person in charge to follow and compliance | 03-31-2023 | -Waiting to get approval from the top management. - The admin listed out and contacted the supplier to provide proper equipment. -Mechenic staff is in charge of installing | Completed
| 11808 | HSE.8-Workers shall be provided with training on the use and maintenance of personal protective equipment. Training shall be upon hire with periodic refresher training offered to all workers. Management will ensure use of PPE as necessary. | Is PPE consistently and effectively used by the workers? - All five workers who were observed operating eyelet snapping machines were not wearing earplugs despite the noise levels (over 80 dBA) requiring hearing protection under the terms of the factory’s risk assessment. | Ensure that workers wear hearing protection when working around loud noise. |  | - Ensure that workers wear hearing protection when working around loud noise. -Train workers about the importance of wear hearing protection. - Assign a person in charge to check and remind team leaders and workers. -Regularly check | 03-31-2023 | OSH officer and OSH collaborator members are in charge to check and remind team leaders to ensure that workers wear hearing protection when working around loud noise. -OSH trains workers about the importance of wear hearing protection. - OSH regularly checks and monitors for this once. | Completed
| 11809 | HOW.1.1-Employers shall comply with all national laws regulations and procedures concerning hours of work public holidays and leave. | Applicable to hours of work and leave is the factory in compliance with the local legal requirements/ FLA Code in all other areas not previously noted? - Workers at the factory exceed legal limits on monthly overtime work. 16 out of 22 sampled workers (across all main work sections) totaled monthly overtime ranging from 41 hours to 104 hours before April 2022 and from 61 hours to 103 hours from April 2022 | (1) Ensure that workers do not exceed legal limits on overtime work. (2) Adjust production planning so that overtime work is not assumed when planning. |  | -Have an accurate attendance recording system -Have a single time record -Keep working time records for at least 12 months -The system should indicate the accumulated overtime over course of the week month and year. -Workers should have access to review | 01-01-1900 | The factory sets up a time recording system indicating the accumulated overtime per week month and year to monitorovertime working hours. -The overtime control is based on legal requirement 30 hours per month and 300 hours per year. But it is very difficult to comply the overtime regulation due to man power shortage and emergent orders.The updated overtime monitoring practice is that before working overtime workers sign the overtime registering form with their consent the form is sent to production leader for checking then sent to HR before 11:00 am. HR staff cross checks the actual over time and the planned overtime of each worker and informs the actual accumulated overtime to the director. The factory is on the way to Improve production planning and schedule to reduce overtime gradually | In Progress
| 11810 | HOW.12.2-The time at which annual leave is taken is determined by employers in consultation with workers taking into account work requirements and the opportunities for rest and relaxation available to workers. | The provision of annual leave is determined by employers in consultation with workersfor example through a leave committee? - (1) There is no annual leave plan established for 2021 and 2022 as required by local law. (2) The factory does not pay out unused annual leave days correctly. As a general practice the factory provides one annual leave day a month. Extra annual leave day | (1) Establish an annual leave plan as per legal requirement. (2-5) Follow local law when calculating and paying out annual leave for workers. |  | -Study the legal requirement - Establish an annual leave plan as per legal requirement. -Works with managements for annual leave plan. -Update to follow local law when calculating and paying out annual leave for workers. - Assign a person responsible for | 03-30-2023 | HR is responsible for this issue. HR studies the legal requirement. -The HR dept establishes an annual leave plan as per legal requirements. -CSR/ HR works with management for the annual leave plans. -CSR/ HR updated to follow the local law when calculating and paying out annual leave for workers. - HR monitors periodically to ensure compliance. | Completed
| 11811 | HOW.21-Other than in exceptional circumstances the total weekly work hours (regular work hours plus overtime including any alternative shifts such as 4x4 or 3x3) shall not exceed 60 hours per week. | Over the past 12 months have all workers' hours been kept under 60 hours per week? - 15 out of 22 sampled workers (across all main sections) worked more than 60 hours in a week reaching up to 72 hours per week during November 2021 and October 2022. | Ensure that workers do not work more than 60 hours per week including by reviewing the factory's workplan and production planning. |  | -Have an accurate attendance recording system -Have a single time record -Keep working time records for at least 12 months -The system should indicate the accumulated overtime over course of the week month and year -Workers should have access to review t | 01-01-1900 | The factory sets up a time recording system indicating the accumulated overtime per week month and year to monitorovertime working hours. -The factory is on the way to Improve production planning and schedule to reduce overtime gradually -Factory will monitor workers not work more than 60 hours in a week as being required by client. | In Progress
| 11812 | ND.3-Recruitment and employment policies and practices including job advertisements job descriptions application and interview questions and job performance/evaluation policies and practices shall be free from any type of discriminatory bias. | Are all employment policies or practices (job advertisement job application job description performance review) free of discrimination in any form? - A recruitment announcement for the factory posted on Facebook in November 2021 stated that applicants should be women between 18-35 years of age. Although the assessment noted that the factory hired workers over 35 years of age in 2021 and 2022 this anno | Do not include restrictions on age gender etc. in recruitment announcements. |  | - Re-check and list out all forms used in the recruitment announcement. -Remove all the restrictions information on age gender etc. in recruitment announcements. -Assign a person in charge to follow the compliance. -Keep regular monitors. | 02-28-2023 | CSR/ HR has the duty to re-check and list out all forms used in the recruitment announcement and then remove all the restrictions information on age gender etc. in recruitment announcements. -HR is in charge to follow the compliance. -HR keeps regular monitors. | Completed
| 11813 | ND.4-Employers may not request the disclosure of any personal non-job related information during the application recruitment or hiring process including but not limited to gender race religion disability sexual orientation nationality political opinion social group ethnic origin or marital status. | Does the factory avoid asking non job related questions during the application recruitment or hiring process? - Forms used during job interviews include personal information unrelated to the job such as marriage status and pregnancy. | Do not request the disclosure of any personal non-job related information during the application recruitment or hiring process. |  | - Re-check and list out all forms used during job interviews -Remove all the disclosure of any personal non-job related information during the application recruitment or hiring process. -Assign a person in charge to follow the compliance. -Keep regula | 02-28-2023 | CSR/ HR has the duty to re-check and list out all forms used during job interviews and then raise out to remove all the disclosure of any personal non-job related information during the application recruitment or hiring process. -HR in charge to follow the compliance and keeps regular monitors. | Completed