## CAP
Repeat | SubformId | Benchmark ID | Benchmark details | Finding details | Recommendation for Immediate Action | Company Plan of Action | Company deadline | Action Taken | Company Progress Status | Repeat
Ongoing
|  |  |  | Member(s) | The Antigua Group, inc |  |  |  |  | Option 3
|  |  |  | Country | Vietnam |  |  |  |  | Option 4
|  |  |  | Date of Inspection | 2021-09-23 |  |  | VIEW:VW_report_CAPaction for action table | Planned | Option 5
|  |  | ID |  |  |  |  | hiddenfields for import | In Progress
Additional CAP Notes
|  | Benchmark ID and details | Question(s) and findingdetails | Recommendation for Immediate Action | Recommendation for Sustainable Improvement | Company Plan of Action | Company deadline (MM-DD-YYYY) | Action Taken | Company Progress Status
| 17220 | C.1.1-Employers shall comply with all national laws regulations and procedures concerning the payment of compensation to workers. | Where salary deductions have happened has the factory made them lawfully and reasonably?Does the factory correctly and legally calculate the payout in terms of the different types of termination (resignation termination with cause or without cause etc.)? - 1. Based on document review termination records annual leave tracking record and interview with factory management; it is noted that the factory does not calculate accurately the annual leave balance for resigned workers. For instance worker A joined on 26th Oct 2007 resigned on 29th April 2021; the factory only paid 8 annual leave days instead of 8.33 annual leave days for this worker [(16/12*4) + 3] = 8.33. This worker had 3 days of annual leave balance in 2020. The factory explained that this mistake was from system calculation when rounding down the decimal. 2. The factory deducts 1.5% of Health Insurance from worker’s wage who are absent from work due to taking sick leave from and above 14 days in a month. In detail worker A took sick leave for 15 days in July 2021 the factory deducted 1.5% of Health Insurance (- VND 57806) from worker’s wage in July 2021 payroll. | 1. Calculate annual leave balance correctly and pay sufficiently for all workers. 2. Ensure that who takes leave due to sickness for at least 14 working days in a month in accordance with regulations of law on social insurance is not required to pay insurance contributions and premiums but still receives benefits from health insurance. |  | 1. Identify the staff member in charge of ensuring correct calculations of annual and sick leave. 2. Ensure that the responsible staff member has received training on annual and sick leave calculations. 3. Pay missing balance to workers identified through the assessment. |  | 1/2022: The annual leave balance is now calculated correctly. Regarding the worker who resigned with 8 paid annual leave days instead of 8.33 due to miscalculation that worker has been paid the appropriate amount. The factory confirmed that a person who takes leave due to sickness for at least 14 working days in a month in accordance with social insurance regulations is not required to pay insurance contributions and premiums but still receives benefits from health insurance. Regarding sick leave calculations the cases identified during the assessment occurred due to miscalculations and the deductions have been repaid to the workers. The factory submitted evidence supporting its remediation work. | Completed
| 17221 | C.7-All payments to workers including hourly wages piecework fringe benefits and other incentives shall be calculated recorded and paid accurately. | Does the management calculate salary payments correctly including all hours of work piece work and other incentives? - Based on payroll and attendance records review during past 12 months interview with factory management and workers; the factory does not provide the correct amount of payment (with extra 100% of hourly rate) during menstruation period (at least 3 days/month 30 minutes/day) to female workers who receive salaries within the hourly rate system. According to law the factory needs to provide 30 minutes breaks daily for 3 days or provide extra payment if the worker does not need to have a break. As current practice of the factory the compensation of menstruation period is paid for piece rate female workers at 2 hours per month. 40% of female workers work with hourly rate 60% of female workers work with piece rate. | Provide menstruation break (at least 3 days/month 30 minutes/day) for female workers or pay the compensation for this period in cases where female workers do not take the break. |  | 1. Identify the staff member in charge of ensuring correct breaks/compensation for female menstruation period. 2. Ensure that the responsible staff member has received training on such breaks/compensation. 3. Provide menstruation break (at least 3 days/month 30 minutes/day) for female workers or pay the compensation for this period if female workers do not take the menstruation break. |  | 1/2022: Factory communicated that it has paid female workers who have piece-rate salary and that for female workers who have hourly salary the factory lets them register monthly. Factory identified responsible staff person (HR Department) and also training for that person. | Completed
| 17222 | ER.3.1-Employers shall provide an orientation to new employees at the time of hiring which includes explanations of the employers’ rules compensation package and policies for human resources grievance systems industrial relations including respect of the right to freedom of association workers’ rights and responsibilities FLA Code of Conduct health and safety and environmental protection. | Does the orientation Training to new workers cover all FLA's Code elements and Employment Functions? (Company Code elements are accepted if FLA Codes are fully covered) - The orientation training includes some general legal information on working hours compensation termination health & safety and workplace rules. However not all FLA Code Elements are included in the orientation training such as harassment and abuse or freedom of association. |  |  | Ensure orientation training covers all Code elements in the FLA Code of Conduct. |  | 1/2022: The factory set up a training program which is in line with the FLA Code of Conduct. The factory conducted orientation training with the updated materials in Nov 2021. | Completed
| 17223 | ER.5.1-Employers shall ensure that all supervisors are trained in national laws workplace regulations and the FLA Code workplace grievance systems and the appropriate practices to ensure compliance. | Does the factory provide any specific training to the relevant supervisors that includes all FLA's Code elements and Employment Functions? - Based on training records reviews and confirmation from factory management it is noted that FLA Code is not included to training for supervisors. The factory management explained that they were not aware of this requirement from FLA. |  |  | Factory shall incorporate FLA Code of Conduct into training for supervisors. |  | 1/2022: The factory now has a training program for supervisors which includes the Code of Conduct. The factory submitted evidence of training in Feb 2022. | Completed
| 17224 | ER.7.1-Employers shall have written policies and procedures with regard to performance reviews that outline the review steps and process demonstrate linkages to job grading prohibit discrimination are provided in writing and seek feedback and agreement/disagreement from employees in writing and that follow all local legal requirements. | Does the factory have policies and procedures on performance reviews that include steps and processes linkages to job grading nondiscrimination written feedback and compliance with legal requirement? 12300ntest - The wage scale is developed with two levels of wage increases for all job positions. However the factory does not have a comprehensive policy/procedure to regulate clearly on how to evaluate the wage level increases (e.g. time criteria terms and condition etc.) |  |  | Factory shall develop a comprehensive policy and procedure to clearly communicate the factory's wage scale. The policy/procedure shall detail how worker performance is evaluated and how worker performance and other relevant criteria relate to wage increases. |  | 1/2022: Factory submitted policy and procedure to clearly communicate the factory's wage scale for leaders/supervisors. At present worker wages are paid in accordance with Vietnamese labor law and worker's skill. Factory is evaluating and developing a policy for workers. The HR Department is responsible for developing the policy for workers. | In Progress
| 17225 | ER.8-Employers shall have written policies and procedures with regard to promotion demotion and job reassignment that outline the criteria demonstrate linkages to job grading and prohibit discrimination or use of demotion or job reassignment as a form of penalty or punishment are provided in writing and seek feedback from employees in writing and follow all local legal requirements. | Does the factory have policies and procedures on promotion demotion and job reassignment? - Based on document review it is noted that the policy on promotion demotion and job reassignment are developed in place. However the policy is simple development. In details: - The promotion policy: there are no clearly criteria terms and conditions to evaluate the employee's performance to be promoted; - The job-reassignment policy: it is based on the Vietnam Labor Law in 2012 which was expired in Jan 2021; Remark: this policy is issued in 2018. |  |  | Enhance the policy on promotion demotion and job reassignment that covers all of the following: 1. Outline criteria 2. Demonstrate linkages to job grading and 3. Prohibit discrimination or use of demotion or job reassignment as a form of penalty or punishment. The policy shall be provided to workers in writing and seek their feedback. The policy shall follow all local legal requirements including the Vietnam Labor Law which is reissued in 2021. |  | 1/2022: The factory will update the policy on promotion demotion and job reassignment by April 2022. | Planned
| 17226 | HSE.14.1-All production machinery equipment and tools shall be properly guarded and regularly maintained. | Do elevators or other mechanical lifting devices have signs that indicate the maximum working load? If lifting equipment is not intended for human transport are there signs stating so?Are compressed gas cylinders used stored and transported properly? - 1. Loading limit of the shelters is posted at the warehouse No. 1 and No. 2 to indicate the maximum working load. 2. No fence equipped to prevent the falling of the gas cylinders in the gas storage at the canteen. | 1. Post loading limit for each shelter. 2. Provide fence/chain for compressed gas cylinders storage to prevent the falling. |  | 1. Post loading limit for each shelter. 2. Provide fence/chain for compressed gas cylinders storage to prevent the falling. |  | 1/2022: 1. Factory provided photo of posted load limit example. 2. Factory provided a chain for the compressed gas cylinder storage to prevent them from falling. | Completed
| 17227 | HSE.1-Employers shall comply with all national laws regulations and procedures concerning health safety and the environment. | Are fire risks assessment results considered and addressed properly?Does it cover all risks and appropriate ways to eliminate and/or control hazards?Is the factory's hazardous waste storage area secure protected clean and sanitized?Applicable to Health Safety and Environment is the factory in compliance with the local legal requirements/ FLA Code in all other areas not previously noted?Are food breaks modified in such a way so that workers can eat their meals while maintaining at least 1 meter distance? - 1. The factory does not conduct fire safety assessment in the facility. 2. The factory has conducted a workplace risk assessment. However a) Risk assessment does not include some areas/sections such as: embroidering section waste water treatment plant waste storage parking lot area. b) The factory does not identify the deadline in-charge person verification for the improvements to reduce or eliminate the risks. 3. The factory does not provide occupational diseases health check for employees who work in conditions with hazards of occupational diseases defined in occupational health and safety record. 4. The latest working condition evaluation (conducted on October 22 2020) did not include ergonomic factor assessment for heavy and hazardous positions as legally required. 5. Two (2) used containers containing paint are used to contain cooling water instead of being stored in the hazardous waste storage. 6. The factory has installed separation screen for each table in the canteen. However employees are separated into group of two persons instead of individually. Besides the distance between individual is less than 2 meters. | 1. The factory is advised to make the fire risk assessment. 2. The factory is advised to identify all hazards and risks at all workplaces/areas and persons to control risks; identify the deadline in-charge person verification for the improvements to reduce or eliminate the risk. 3. The factory is advised that workers working in conditions with the hazards of occupational diseases shall be provided a health check every 6 months. 4. The factory is advised that working condition evaluation shall carry out for all harmful factors in all areas potentially affecting the employee. 5. The factory is advised to ensure all hazardous wastes to be classified labelled properly and stored in the designated area. 6. The factory is advised to practice social distancing measures e.g. install separation screen and keep the distance at least 2 meters. |  | 1. Factory shall conduct a fire risk assessment. 2. Factory shall identify risks and hazards in all areas of the workplace (including embroidery waste water treatment plant waste storage and parking lot) and shall make corrective action plans for necessary improvements. The corrective action plans shall require identifying responsible persons setting deadlines for improvements and collecting verification of improvements. 3. Workers working in conditions with risks of occupational diseases shall have a health check every 6 months. 4. In evaluating working conditions the factory shall include evaluations of ergonomics with attention to those with heavy and hazardous conditions. 5. All hazardous wastes must be classified labelled properly and stored in the designated area. The factory shall address the paint containers that were observed during the assessment. 6. In the canteen factory shall ensure that individual employees are separate by screens and shall keep workers at least 2 meters in distance from one another. |  | 1/2022: 1. Factory conducted fire safety risk assessment in Sept 2021. 2. Factory submitted risk assessment for all areas of the workplace. 3. Factory submitted policy requiring health checks every 6 months for appropriate workers. 4. Factory submitted documentation showing evaluation of ergonomics. 5. Factory submitted photos regarding the containers proper storage of containers including paint containers. 6. Factory submitted photo of new arrangement in canteen with appropriate screens and distancing. | Completed
| 17228 | HSE.14.2-Workers shall receive training in the proper use and safe operation of machinery equipment and tools they use. | Does the factory provide safety training to designated workers with special/high-risk responsibilities (working with laser radiation or electrical issues confined space lockout/tagout work at heights)? - The factory does not provide occupational health and safety (OSH) training for two workers working at height over 2 meters which is required by law. These workers defined as group 3 in law. | Provide required OSH training for designated employees. |  | Provide required OSH training for workers working at heights over 2 meters. |  | 1/2022: The factory held a training course on December 12 2021 for workers working at heights over 2 meters. | Completed
| 17229 | HSE.17.1-Workstations including seating and standing arrangements and reach required to obtain tools shall be designed and set-up in such a manner as to minimize bodily strains. | Is the factory taking proactive steps to reduce repetitive-motion stress or injuries (breaks adjustable workstations)? - Approximately 10% of provided chairs at the sewing section do not have back-support. They are also not adjustable to fit with worker’s working position. | Provide adjustable chairs with back supports for all sewing section workers and take proactive steps to reduce repetitive-motion stress or injuries e.g. providing breaks. |  | Provide adjustable chairs with back supports for all sewing section workers and take proactive steps to reduce repetitive-motion stress or injuries (e.g. by providing breaks). |  | 2/2022: In conversations with supplier Antigua learned that some workers prefer seating without backs so that they can move easily around the area. | Completed
| 17230 | HSE.19-All facilities including workplace buildings toilets canteens kitchens and clinics shall be kept clean and safe and be in compliance with all applicable laws including relevant sanitation medical and safety and health regulations. | Does the factory provide adequate soap and drying facilities in the bathroom? - There are no hand drying facilities or tissues provided at the toilets. | The factory is advised to provide tissue or hand drying facilities at the toilets. |  | The factory shall provide tissues or hand drying facilities in the restrooms. |  | 1/2022: The factory has provided tissues in the workers' restroom and provided photo evidence. | Completed
| 17231 | HSE.4.1-Employers shall at all times be in possession of all legally required and valid permits and certificates related to health safety and environmental issues such as: Purchase and storage of chemicals; Fire safety inspections; Machinery inspections; Waste disposal; Environmental licenses/permits;Sanitation permits including those required for canteens; and Vehicle inspection and driver permits for all employer provided transportation. | Does the factory have all legally required permits and certificates related to health safety and environment aspects? - The factory has not conducted the legal inspection of the air distribution system (from the compressor tanks) as legally required. | Ensure that air distribution system (from the compressor tanks) is inspected and certified as legally required. |  | Ensure that the air distribution system from the compressor tanks is inspected and certified. |  | 1/2022: The factory has arranged for an inspection of the air distribution system from the compressor tanks on March 31 2022. | Planned
| 17232 | HSE.5.1-All applicable legally required or recommended elements of safe evacuation shall be complied with including all of the following elements: posting evacuation plans; the installation and maintenance of fire alarms; the installation and maintenance of emergency lighting; ensuring aisles/exits are not blocked and that workers are not blocked within their workstations; employee education and training; and evacuation procedures and fire drills. | Are emergency exits clearly marked? - One main exit aisle at automatic sewing section is only marked on one side instead of both sides leading to the emergency exit door. | Ensure that all emergency exits are clearly marked. |  | Ensure that the main emergency exit aisle is clearly marked on both sides. |  | 2/2022: Factory provided photo of emergency exit aisle with clear marks on both sides. | Completed
| 17233 | HSE.5.1.4-All applicable legally required or recommended elements of safe evacuation shall be complied with including all the following: ensuring aisles/exits are not blocked and that workers are not blocked within their workstations | Are emergency exits free from obstruction? - 1) One emergency exit is partially obstructed by materials at the cutting area. 2) At least two emergency call points (fire alarm buttons) are obstructed by materials and tubs at the cutting section and kitchen area. | 1) Keep emergency exits free from any obstructions all the time. 2) The factory is advised that emergency call points (fire alarm buttons) shall be kept free from any obstructions. |  | 1. Clear the emergency exit in the cutting area. 2. Ensure unobstructed access to the emergency call points in the cutting and kitchen areas. |  | 1. Factory submitted photo of cleared emergency exit. 2. Factory submitted photo of unobstructed access to emergency call points. | Completed
| 17234 | HSE.5.3-Alarm systems shall be regularly tested and evacuation drills shall be undertaken at least annually. | Do all workers including all shifts participate in a full evacuation drill at least annually? - Two latest evacuation drills are conducted on June 20 2020 (with fire police) and December 26 2020 (internal). Therefore the factory does not: a) Practice fire drill according to fire prevention plan (i.e. fire drill with fire police) during the past 12 months as legally required. b) Conduct fire drill at least annually as required by FLA. | Conduct fire drill according to fire prevention plan (fire drill with fire police) annually. |  | 1. Identify staff responsible for ensuring annual fire drills. 2. Confirm that staff person has received sufficient training on fire drill requirements. 3. Conduct fire drill according to fire prevention plan (fire drill with fire police) on an annual basis. |  | 1/2022: 1. Factory identified responsible staff (HR Department). 2. Factory confirmed training on fire drill requirements. 3. The fire drill was conducted with fire police in Dec 2021. Antigua is awaiting factory's confirmation of the responsible staff person and that the person has received appropriate training. | Completed
| 17235 | HSE.5.4-The emergency evacuation plan (EEP) includes procedures for notifying local community authorities in case of accidental discharge or release of chemical/waste products or any other environmental emergency. | Does the factory have an appropriate system to respond to any unexpected environmental emergency such as chemical spills or gas leak? - The factory has not conducted chemical spill response drill practice during the past 12 months according to the company’s procedure. The latest drill practice was conducted in August 2020. | The factory is advised to conduct chemical spill response drill annually according to the company’s procedure. |  | 1. Identify staff responsible for ensuring annual chemical spill response drill. 2. Confirm that staff person has received sufficient training on chemical spill response drill requirements. 3. Conduct chemical spill response drill on an annual basis. |  | 1/2022: 1. Factory identified person responsible. 2. Factory provided evidence of training. 3. The factory conducted a chemical spill response drill in Dec 2021. | Completed
| 17236 | HSE.6.1-All safety and medical equipment (e.g. fire fighting equipment first aid kits) shall be available in sufficient numbers throughout the workplace maintained and stocked as prescribed and easily accessible to workers. | Does the factory have a suffient number of fire extinguishers?Are fire extinguishers: placed at the correct locations marked easy to access and in good conditions?Does the factory have sufficient and adequate fire fighting equipment (fire extinguishers hoses sprinkler system fire pump)?Are firstt aid kits located throughout the factory and easily accessible to workers? - 1. The mezzanine of sewing section has an area of around 520 meters and used to store sewing machines. However there are 5 instead of at least 7 fire extinguishers equipped in this area as legally required. 2. One fire extinguisher is obstructed by industrial waste at the industrial waste storage. 3. All (five) fire extinguishers are not inspected visually on a monthly basis due to lack of necessary monitoring. The latest inspection was conducted in April 2021. 4. The valuation of design on fire prevention and fighting of the factory was approved in 2016. According to the valuation the factory shall install sprinkler system. However the automatic fire fighting system (sprinkler system) has not been installed and the factory has not obtained the fire safety acceptance. 5. One first aid kit is obstructed by materials at the cutting area. | 1. Equip fire-extinguishers sufficiently. 2. Keep fire extinguisher free from any obstructions. 3. Inspect fire extinguishers monthly. 4. The factory is advised to: a) Ensure that the automatic fire fighting system to be installed according to the valuated fire safety design. b) Ensure the fire-fighting system shall be inspected and accepted by the Fire Department to obtain the fire safety acceptance. 5. Keep first aid kits free from any obstructions. |  | 1. Identify staff responsible for fire safety. 2. Ensure responsible staff are properly trained on all fire safety requirements. 3. Conduct regular fire safety risk assessments at the factory and develop corrective action plans to address any risks and noncompliances. 4. Add 2 fire extinguishers in the mezzanine of the sewing section. 5. Keep fire extinguisher free from any obstructions. 6. Inspect fire extinguishers on a monthly basis. 7. The factory shall ensure that the automatic fire fighting system is installed according to the fire safety design. Factory shall ensure that the fire-fighting system is inspected and accepted by the Fire Department. 8. Keep first aid kits free from any obstructions. |  | 10/2021: 1. Factory identified the person responsible for fire safety (i.e. Captain). 2. Factory provided evidence of training. 4. Factory has 7 extinguishers in the mezzanine of the sewing section (2 extinguishers were added). 5. Factory provided photo evidence of remediation. 6. Factory provided photo evidence of remediation. 7. Factory was constructed in 2008. For buildings A B C E F G the factory has Fire Acceptance Protection (2008) and Fire Protection Certificate (2011) granted by the fire police department of Ha Nam province. Up to now the fire police department of Ha Nam does not require the factory to install the sprinkler system according to yearly minutes of the fire protection system check. The factory will install the sprinkler system when the fire police department require. The design that was submitted regarding fire prevention was meant for a new project. However this project has been temporary suspended therefore the factory will implement the revise plan only when the project is reinstated. 8. Factory provided photo evidence of remediation. | Completed
| 17237 | HSE.6.2-A sufficient number of workers shall be trained in first aid and firefighting techniques. Training shall be upon hire and with periodic refresher training. | Do a sufficient number of workers know how to use the fire extinguishers?Are workerstrained on procedures concerning the provision of firstt aid?Do workers with specific additional firefighting emergency and firstt aid responsibilities receive training so they can effectively execute their duties (e.g. brigade members)? - 1. The factory appoints a fire brigade with 30 members including one captain and one vice-captain instead of at least two vice-captains as legally required. 2. The factory does not conduct the first aid training for all workers on an annual basis. The latest training was conducted on September 8 2020. 3. Based on training records payroll and attendance records review during past 12 months interview with factory management and workers; it is noted that the training records of the factory are not reliable and consistent with actual working time of workers. For instance: - Worker A: piece rate salary. The training record of Group 6 on 3rd Oct 2020 (8 hours). However this worker still has productivity output in the same day. - Worker B: piece rate salary. The training record of First Aid on 5th Oct 2020 (8 hours). However this worker still has productivity output in the same day Due to this inconsistency the training records of the factory are not reliable for reference during the assessment time. | 1. Ensure the fire brigade's organization to meet the legal requirement 2. Provide first aid training for all workers on time as legally required. 3. The factory is advised to ensure the training records are matched with the actual practice of worker’s working time. The training courses are provided to all required workers as legally required. |  | 1. Ensure that the fire brigade has two Vice-Captains. 2. Identify the staff responsible for providing annual first aid training. Provide first aid training for all workers on an annual basis. 3. Identify the staff responsible for ensuring correct training records. Ensure that training attendance is correctly collected and that all workers are trained as legally required. |  | 1/2022: 1. The fire brigade has been appointed and is comprised of 30 persons including 1 Captain and 2 Vice-Captains. 2. Factory identified the individual responsible for first-aid training. 3. The factory communicated that it organized a training course on occupational safety and health in compliance with the law for all members of the factory. However some workers did not attend the training course as planned. Instead those workers were still working and attendance was not accurately recorded. Training was held again in Nov 2021 and factory submitted evidence of training. | Completed
| 17238 | HSE.8-Workers shall be provided with training on the use and maintenance of personal protective equipment. Training shall be upon hire with periodic refresher training offered to all workers. Management will ensure use of PPE as necessary. | Does the factory provide training to all workers regarding PPE usage and maintenance? - The factory provides orientation training for new employee in around one (1) hour instead of at least 16 hours. Besides the orientation training does not include the first aid skill training as legally required. | The factory is advised to provide OSH in sufficient training hours including first aid training. |  | Provide sufficient orientation training (16 hours). Orientation must include first-aid skills training. Factory shall submit orientation training materials including topics and duration. |  | 2/2022: Factory submitted evidence of training. | Completed
| 17239 | HOW.10.1-Employers shall provide workers with all official public holidays as required under national laws regulations and procedures. | Are the workers provided all the public holidays as required by law? - Based on document review termination records and interview with factory management; the factory did not pay the payment of public holiday (Hung King’s death anniversary) on 21st April 2021 for resigned workers. For instance the factory issued the terminated decision on 29th April 2021 for worker A however there was no payment of public holiday for this worker in April 2021. Factory explained that this worker took unpaid leave many days in Aprils hence the factory did not count public holiday. | Provide payment of public holiday sufficiently for resigned workers as legally required. |  | Provide holiday payment to the resigned worker. |  | 1/2022: The additional holiday payment to the resigned worker was made as legally required. | Completed
| 17240 | HOW.21-Other than in exceptional circumstances the total weekly work hours (regular work hours plus overtime including any alternative shifts such as 4x4 or 3x3) shall not exceed 60 hours per week. | Over the past 12 months have all workers' hours been kept under 60 hours per week? - Based on payroll and attendance records review during past 12 months interview with factory management and workers; 1. There are approximately 153 workers in July 2021 and 26 workers in August 2021 who work more than 40 overtime hours/month which are excessive than limitation of monthly overtime as legally required. The maximum overtime hours are 67.49 hours/month. 2. There are approximately 4% of total workforce work more than 60 hours/week (including regular + overtime hours) which is excessive the weekly hours as FLA Benchmark. The excessive weekly hours are happened in July & August 2021 from one to three weeks/month. | 1.Ensure that the number of overtime working hours of the employees do not exceed 40 hours in a month as legally required. 2. Ensure that weekly working hours is not more than 60 hours/week as required by FLA Benchmarks. |  | Factory shall provide detailed plan of how to ensure that weekly working hours and overtime working hours do not exceed legal limits. The plan shall include specific timelines and identify responsible staff. |  | 2/2022: Factory aims to always comply with the law (production with the OT not exceeding 40hrs/week in the peak season (factory provided evidence). However from July-August 2021 was a period that the factory was affected by COVID 19. Many workers could not come to work therefore the factory needed more overtime than usual to meet delivery deadlines. This situation is a result of the COVID 19 pandemic. | Planned