## CAP
Repeat | SubformId | Benchmark ID | Benchmark details | Finding details | Recommendation for Immediate Action | Company Plan of Action | Company deadline | Action Taken | Company Progress Status | Repeat
Ongoing
|  |  |  | Member(s) | New Balance Athletics Inc. |  |  |  |  | Option 3
|  |  |  | Country | Indonesia |  |  |  |  | Option 4
|  |  |  | Date of Inspection | 2017-08-10 |  |  | VIEW:VW_report_CAPaction for action table | Planned | Option 5
|  |  | ID |  |  |  |  | hiddenfields for import | In Progress
|  |  | Additional CAP Notes | New Balance production ended at this factory in March 2019. The decision was due to business reasons. The factory had remediated or was in process of remediating all issues uncovered. The factory was also a member of an international program focused on respecting labor rights that monitors factory working conditions.
|  | Benchmark ID and details | Question(s) and findingdetails | Recommendation for Immediate Action | Recommendation for Sustainable Improvement | Company Plan of Action | Company deadline (MM-DD-YYYY) | Action Taken | Company Progress Status
| 14561 | C.6-All wages including payment for overtime shall be paid directly and in full within legally defined time limits. When no time limits are defined by law compensation shall be paid at least once a month. | 7 - 1. The factory&rsquos payroll does not reflect the actual working hours records and there is no working mechanism for accurately linking payroll with the working hours records. The factory practices double bookkeeping with an official printed computerized time record and an additional separate paper time card to record overtime indicating that the factory management tries to hide excessive working hours beyond the legal limit and rest days. A review of 40 samples of payroll and time records (with 10 paper time cards found) revealed several discrepancies and excessive overtime as a systematic issue. C.5 C.6 2. 2. The payroll records of a sewing operator from line 11 showed an overtime wage of IDR 2163962 (USD 164.34) in March 2015 for working 74.5 hours of overtime per month. However based on a separated paper time card combined with the printed computerized time record the worker worked a total of 101 overtime hours in March 2015. Therefore the worker should have received a total wage at IDR 3140625 (USD 238.51)as per legal overtime rate. Thus there was a wage discrepancy of a total of IDR 976663 (USD 74.17) for the March 2015 payroll. C.7 C.15 ER.23.4 ER.23.5 3. The payroll records of a sewing operator from line B 9 showed an overtime wage of IDR 2302023 (USD 174.83) in March 2015 for working 79 hours of overtime per month. However based on a separated paper time card combined with the printed computerized time record the worker worked a total of 84.5 hours of overtime in March. As a result the worker should have received IDR 2762429.5 (USD 209.87) as per legal overtime rate. Thus there was a wage discrepancy of IDR 460406.5 (USD 34.97) for this worker in March 2015. C.7 ER.23.4 ER.23.5 4. There are 22 security guards (Female: 8 Male: 14) directly hired from the contracting security agency. The outsourced security guards are paid through their agency and do therefore not have a direct employment relationship with the factory. The outsourced security guards receive a wage of IDR 1500000 /month (USD 113.92) for newly hired security guards during their first 3 month and IDR 2300000/month after 3 months (USD 174.67) which is below the legal minimum wage IDR 2700000/month (USD 205.05). Moreover outsourced security guards are paid the normal daily wage for working on their rest day which is considered overtime. They are paid overtime at a rate of IDR 10000/hour flat (USD 0.76) instead of the legal overtime rate of 150% for the 1st hour 200% for consecutive hours for overtime on regular days and 200% for working on rest days. C.2 5. All workers were required to go home earlier at 12:00 noon on October 26 2015 due to an electrical shut down. However they were paid only the 4.5 hours of work and not the rest of 3.5 hours. Although factory management stated that there was an electrical shut down there was no record to confirm the incident such as a letter from local authority. As per local law the employer is obliged to pay the full wage for workers in the case of a work stoppage due to an employer&rsquos own fault or because of impediments that the entrepreneur should have been able to avoid. HOW.19 6. Workers are approved by the supervisor chief or Human Resources to go home earlier due to sick at the factory are not paid full day. The factory paid only the hours of worked violating legal requirements that state that the worker shall be compensated the full day. For example: a worker received the recommendation from the onsite clinic to go home at 10:00 AM on October 16 2015 due to sickness. However he only received the wage for 2.5 hours of worked (7:30 AM to 10:00 AM) instead of full day wage for his sick leave. HOW.16 7. Based on contribution of the employer&rsquos healthcare program BPJS for November 2015 651 out of 1939 employees (around 33.57% of employees) are not registered with the legally required healthcare program BPJS. In addition outsourced security guards are not registered to receive social security guards and healthcare program Badan Penyelenggara Jaminan Sosial BPJS. ER.22 1. Finding Status: Remediated Explanation: Based on document review management and worker interviews it is noted that the factory’s payroll records reflect all actual working hours records. The working hours records link with payroll records. All overtime hours including rest day hours are recorded in payroll record and matched with the number of overtime hours on time records. 2. Finding Status: Remediated Explanation: Based on document review it is noted that the factory had paid the deficiencies overtime wages that happened in March 2015. 405 employees had been paid for their extra overtime hours on March 21 2015 ranging from IDR 40000 (USD 2.96) to IDR 202900 (USD 15.02) and 342 employees had had been paid for their extra overtime hours on March 22 2015 ranging from IDR 120000 (USD 8.88) to IDR 346500 (USD 25.64). Total overtime compensation paid by factory for deficient wages in March 2015 was IDR 132414000 (USD 9941). 3. Finding Status: Remediated Explanation: As explained above it is noted that the factory had paid all the deficiencies overtime wages that happened in March 2015 to the relevant workers. 4. Finding Status: Remediated Explanation: Based on record of payment settlement for wage deficiencies of outsourced security guards dated on December 7 2016 it is noted that all 22 outsourced security guards had received back pay for wage deficiencies that happened for periods of January 2015 to December 2015. The amount of back pay ranging from IDR 2222319 (USD 164.46) to IDR 28515086 (USD 2110.2) /person in a total of IDR 353.476152 (USD 26538) paid by factory. The outsourced security guards received the payment on November 25 2016 at the factory witnessed by the security labor agency (PT Bintang Eca Pratama) and a Lawyer appointed by factory. It is noted that the wages were correctly calculated and paid. The factory had discontinued using security guards from labor agency and started from March 2017 all security guards are directly hired by factory. 5. Finding Status: Remediated Explanation: Based on back pay record for the case of workers who were required to go home early at 12:00 noon on October 26 2015 due to an electrical shut down it is noted that the factory had paid the rest of the 3.5 hours wage deficiency a sum of IDR 39400 (USD 2.92) for each worker on July 27 2016. Total wages paid by factory for this case is IDR 73992300 (USD 5554) for 1875 total employees. There has not been any other incident of electrical shut down since. 6. Finding Status: Remediated Explanation: Based on document review management and worker interviews it is noted that workers who are ill at the factory and go home are paid for a full day. 7. Finding Status: Partially Remediated Explanation: It is noted that the factory has registered majority of employees including security guards into Healthcare insurance program BPJS. However there are still around 19 employees that have not been registered with the legally required healthcare program BPJS. ER.22 Root Causes: HR department has difficulties to register worker who are still under other subsidiary of healthcare insurances by the Government such as: Jamkesmas Jamkesda etc. | 1. Ensure all overtime hours are correctly paid at the legal overtime rate. Cease the practice of double bookkeeping and keep one single electronic time record system. Regularly train and communicate workers on their rights of legal overtime rate and correct compensation.2. Ensure that all outsourced security guards are paid the legal minimum wage.3. Pay all outsourced security guards directly. If this is not feasible ensure that there is a verifiable payment system for contracting workers and monitor the payment system to ensure that contracting workers are paid accurately including minimum wage requirements proper wage deductions and timely payments. Ensure thatcontracting security guards receive at least the legal minimum wage and are paid the legally required overtime rate for work done on rest days and regular overtime. Establish guidance documents for contracting agencies that include the FLA benchmarks. 4. Retroactively reimburse all workers for all discrepancies due to inaccurate time and pay records over the last 12 months. Ensure that all eligible workers receive the discrepancies between the actual legal overtime rate amount and the wage they received. Revise the wage and time record system to ensure that all working hours are paid accurately as per legal requirements. Regularly train and communicate the workers on their rights the legal overtime rate and revisions regarding the wage and time record system. 5. Retroactively compensate all contracting security guards the discrepancies between their legally entitled overtime rate amount and the wage they received for the last 12 months.6. Retroactively compensate the full amount of day&rsquos work to workers that had to leave work on the day of the electrical shut down as per legal requirements. Ensure that all workers are accurately and fully compensated for work stoppages that workers cannot be held accountable for but are at the employer&rsquos fault. 7. Provide sick leave with full wage as legally required. 8. Register all employees to receive the healthcare program BPJS. 1. Ensure all overtime hours are correctly paid at the legal overtime rate. Cease the practice of double bookkeeping and keep one single electronic time record system. Regularly train and communicate workers on their rights of legal overtime rate and correct compensation.2. Ensure that all outsourced security guards are paid the legal minimum wage.3. Pay all outsourced security guards directly. If this is not feasible ensure that there is a verifiable payment system for contracting workers and monitor the payment system to ensure that contracting workers are paid accurately including minimum wage requirements proper wage deductions and timely payments. Ensure thatcontracting security guards receive at least the legal minimum wage and are paid the legally required overtime rate for work done on rest days and regular overtime. Establish guidance documents for contracting agencies that include the FLA benchmarks. 4. Retroactively reimburse all workers for all discrepancies due to inaccurate time and pay records over the last 12 months. Ensure that all eligible workers receive the discrepancies between the actual legal overtime rate amount and the wage they received. Revise the wage and time record system to ensure that all working hours are paid accurately as per legal requirements. Regularly train and communicate the workers on their rights the legal overtime rate and revisions regarding the wage and time record system. 5. Retroactively compensate all contracting security guards the discrepancies between their legally entitled overtime rate amount and the wage they received for the last 12 months.6. Retroactively compensate the full amount of day&rsquos work to workers that had to leave work on the day of the electrical shut down as per legal requirements. Ensure that all workers are accurately and fully compensated for work stoppages that workers cannot be held accountable for but are at the employer&rsquos fault. 7. Provide sick leave with full wage as legally required. 8. Register all employees to receive the healthcare program BPJS. |  | 1. It is noted that the factory has registered majority of employees including security guards into Healthcare insurance program BPJS. However there are still around 19 employees that havenot beenregisteredwiththelegallyrequiredhealthcareprogramBPJS. 2. Since September 1 2017Factory outsourcedgatehouse security guards toindependent third partyandwill ensurethey follow the regulations for shift working hours overtime payment and National Health Care. The 19 security guards have been registered into Healthcare by Security Guard Company on Oct. 2017 their BPJS have activeonDecember 2017. | 12-31-2017
| 14562 | C.6-All wages including payment for overtime shall be paid directly and in full within legally defined time limits. When no time limits are defined by law compensation shall be paid at least once a month. | 6 - 1. Based on document review it is noted that new workers who do not pass the five day probation period are paid a daily rate of IDR 111858 (USD 8.25) which is the monthly minimum wage IDR 3355750 (USD 248.34) divided by 30 instead of daily rate IDR 159797 (USD 11.83) which is the monthly minimum wage divided by 21. C.1 C.2 C.3 2. Based on document review it is noted the formula in the payroll system wrongly calculated overtime wage when the workers have unpaid leave in a month. For example: A worker had four days absent (unpaid leave)and she worked overtime for 81 hours in July 2017. She is supposed to get overtime wage IDR 1573593 (USD 116.45) instead of IDR 1572914 (USD 116.4) as indicated in payroll record. Thus overtime deficiency of IDR 679 (USD 0.05) occurred on this worker. Moreover total pay is rounded down when net wage amounts to below IDR 50 such as IDR 4975149 (USD 368.18) became IDR 4975100 (USD 368.17). C.5 C.7 3. The contribution of social insurance (Old Age Security and Retirement Guarantee) is calculated from basic wage instead of basic wage plus fixed allowance. ER.22 0 | Compensate correct daily rate to new workers who do not pass probation period using the formula: minimum wage divided by 21. Ensure all overtime wages are correctly calculated adjust the net wage to be rounded up instead of rounding down. Calculate contribution of social insurance from actual monthly wage (basic wage plus fixed allowance). Compensate correct daily rate to new workers who do not pass probation period using the formula: minimum wage divided by 21. Ensure all overtime wages are correctly calculated adjust the net wage to be rounded up instead of rounding down. Calculate contribution of social insurance from actual monthly wage (basic wage plus fixed allowance). |  | 1.a. Factory has changed the calculation formula by dividing the minimum wage by 21 days for probation workers starting from November 2017. 2.a. Factory has contacted our 3rd Party payroll provider to re-program all calculation formulasto ensure exact correct payment amount is reflected.In the event that actual amount requires rounding programmer has been instructed to Round Up in favor of employees.Factory will no longer round down. Starting from November 2017 every decimal will be round up to Rp. 100. 3.a. Factory will apply the new calculation formula : basic wage plus fixed allowance to calculate the Old Age Security and Retirement Guarantee starting from January 1 2018 .
| 14563 | XX.1-Please refer to the assessment report for benchmark information. For assessments conducted prior to 2020 benchmark numbers reflect the FLA’s 2011 Workplace Compliance Benchmarks. | 1 - 1. There is no procedure to enable workers to raise concerns regarding Health Safety and Environmental Protection. In addition there are no procedures to protect workers who allege environmental or Health &amp Safety violations. ER.31 2. There is no procedure for reporting environmental emergencies. ER.313. The factory does not arrange specific training to supervisors regarding Environmental Protection. ER.17 4. The factory has not arranged for an inspection by the Environmental Department in order to obtain the legally required permit for the storage of hazardous waste. HSE.2 HSE.4 1. Finding Status: Partially Remediated Explanation: The factory has a procedure that enables workers to raise concerns regarding Health Safety and Environmental Protection (RSK-P-HRD-012 issued on January 29 2016 and revised on February 15 2016) however the procedure overlaps with raising concerns regarding Industrial Relations the procedures are not specific to Health Safety and Environment. Hence there is no clear step on the timeline for the responsible HSE person to take action after receiving concern raised by worker what step needs to be taken after the concern has been investigated and whether the worker is able to refuse to work before the conditions are remediated. ER.31 HSE.1 Even though the procedure to protect workers who allege environmental or Health & Safety violations is stated in RSK-P-HSE-019 issued on January 29 2016 point 3.1.3 factory management must provide protection guarantee to workers who report situation on their workplace from intimidation. ER.31.2.6 Root Causes: No annual review conducted periodically. The last review was on February 15 2016 and no further review conducted. Furthermore the person who create and revised the procedure has already resigned on June 2016 and no one has replaced the position. 2. Finding Status: Not Remediated Explanation: Current procedure for reporting environmental emergencies (RSK-P-HSE-019 issued on January 29 2016) has not clearly stated steps to report any environmental emergencies (flow chart) and to whom workers shall report any environmental emergencies occurrence and how long (time frame) the person in charge will handle the concern. HSE.1 ER.31.2.5. Root Causes: No annual review conducted periodically. The last review was on February 15 2016. Furthermore the person who create and revise the procedure resigned on June 2016 and no one has replaced that position). Furthermore current HSE officers handle many aspects at the factory (HSE C-TPAT Technical) which creates time constraints in allowing for procedure review. 3. Finding Status: Partially Remediated Explanation: The factory has arranged specific training to supervisors regarding Environmental Protection however this training has not been conducted for each supervisor at the factory since the following: November 18 2016 for 24 out of 59 supervisors July 11 and 13 2017 for 42 out of 59 supervisors. ER.17.1 ER.17.2. Furthermore based on attendance lists of trainings in 2016 and 2017 none of the attendees have had refresher trainings on these specific trainings. ER.17.3. Root Causes: The tight production schedule made this training only available to supervisors who were able to attend. 4. Finding Status: Partially Remediated Explanation: The factory has the legally required permit for the storage of hazardous waste from DKI Jakarta One Gate Service and Investment Bureau on March 27 2017 up to March 23 2020. However there is no inventory record or disposal record that has been reported to DKI Jakarta Governor c.q. North Jakarta Province BLH Bureau Head and DKI Jakarta Mayor u.p. North Jakarta BLH Head which is legally required every 3 months. HSE.2 HSE.4 Root Causes: There is no awareness that hazardous waste disposal and inventory records should be reported every 3 months to local governments. Additionally no one has read the permit for the storage of hazardous waste which requires the factory report hazardous waste. | 1. Arrange for the legally required inspection by the Environmental Department in order to obtain the permit for the storage of hazardous wastes from the local Environmental authority. 1. Arrange for the legally required inspection by the Environmental Department in order to obtain the permit for the storage of hazardous wastes from the local Environmental authority. |  | 1.Factory will createspecificprocedures with annual reviews for any persons to raise HSE concerns.Procedures will include clear and easy to follow flow chart diagram describing entire procedure for any persons to raise HSE concerns and committed timeline over actionable items for HSE responsible person.Factory will not force anyone to perform any work in dangerous or hazardous conditions. 2.Factory will createspecificprocedureswith annual reviewsfor any persons to report environmental emergencies.Procedures will include clear and easy to follow flow chart diagram describing entire procedure for any persons to environmental emergencies and committed timeline over actionable items for factory designated responsible person.Training will be provided to all supervisors 3.Environmental protectiontraining will be provided for all supervisor 4.Factorywillmake record waste disposal and inventory then will report to local government every 3 month
| 14564 | HSE.1-Employers shall comply with all national laws regulations and procedures concerning health safety and the environment. | 2 - 1. There has been no fire risk assessment conducted by the factory. HSE.5 2. The factory has not posted any evacuation plans in the fabric warehouse packing section and finished goods warehouse of production building #1 and production building #2. In addition the evacuation plan posted inthe sample and sewing section of production building #2 does not reflect the actual physical layout of the evacuation routes since the arrow signs on the evacuation plan do not match the actual route to the nearest assembly point. HSE.5 3. The factory only installed one emergency exit in the finished goods warehouse while the total area of finished goods warehouse is around 1000 sqm. In addition one exit door in the sample section one exit door in the press room and one exit door in production building #1 do not open in the direction of evacuation. HSE.5 4. All emergency alarms in production building #1 and production building #2 are not equipped with a battery. In addition the factory does not have a centralized battery sufficient to covering all emergency alarms. HSE.5 5. The factory has not installed any emergency lighting in the corridors leading to the emergency exits and assembly points in production building #1 production building #2 and boiler room production building #2. HSE.17 6. The factory has not established any procedures with steps on how to ensure that all special categories of workers safely evacuated as legally required. HSE.17 7. The mesh metal cutting gloves used by three cutting operators in the cutting department have holes on the fingertips. HSE.7 1. Finding Status: Not Remediated Explanation: Factory has not conducted internal fire risk assessment nor commissioned it to third party expert.HSE.5 Root Causes: Factory thought that Critical Life Safety audit through visual way by Vanity Fair – Asia Inspection was a fire risk assessment while in actuality it is not. 2. Finding Status: Not Remediated Explanation: There is no arrow sign marked on the floor in the pressing area while arrow signs on floor in the alley of the south gate is blurred. Furthermore there is no evacuation map posted in the pressing area. HSE.5 Root Causes: The evacuation map has not been updated due to the lay out change and the authority to implement HSE has to be approved by the General Manager before being implemented. The OHS team has not scheduled to repaint the blurred arrow signs. 3. Finding Status: Partially Remediated Explanation: The factory has provided another emergency exit in the finished goods warehouse. The door on the second floor in building #1 from sample room to production already swings outward. The press room has been renovated into an open space thus no door is needed. Furthermore one main exit door in production building #2 also swings outward without any obstruction. However there are several matters which expose workers to fall hazards since: There is floor height difference between boiler/compressor room floor with finished goods areas floor that directly lies in front of boiler/compressor room and there is a door sill at boiler/compressor room that might trip workers when they’re in a rush to exit. HSE.5 Even though the door on the second floor at building #1 from sample room to production swings outwards it directly opens to stairs without a platform which runs the risks of people who walk upstairs accidently hit by person who opens the door from the inside and exposes people who seek egress route from second floor to ground floor during emergency with fall hazard. HSE.5 Root Causes: The height difference and door sill is not an apparent concern for the factory as this was never pointed out by external auditors. Currently the HSE officer is still under the process of finding the best solution for relocating the door in the sample room without affecting room temperature (if the door is simply removed) or affecting the stairway degree (if widening the platform). 4. Finding Status: Partially Remediated Explanation: Emergency alarms in production building #1 and production building #2 are equipped with UPS (Uninterrupted Power Supply) there is an UPS for each building. However there is no functionality test upon fire alarm as per manufacture standard to ensure fire alarm is still functioning during electrical black-out. HSE.5.3 Root Causes: There is no awareness that functionality test shall be made for its functionality and it should be as per manufacture standards. 5. Finding Status: Remediated Explanation: The factory has installed emergency lighting in the corridors leading to the emergency exits and assembly points in production building #1 production building #2 and boiler room production building #2. HSE.5.1 6. Finding Status: Remediated Explanation: The factory has established procedures with steps on how to ensure that all special categories of workers safely evacuated (RSK-P-HSE-010). HSE.1 HSE.5. 7. Finding Status: Remediated Explanation:None of cutters at production building #1 are wearing mesh gloves with holes. All mesh gloves worn by cutters are in acceptable condition. HSE.7 HSE.8. | 1. Arrange for a third-party to conduct a fire risk assessment. 2. Post evacuation maps with the correct layout of the evacuation routes in all areas of thebuilding. 3. Provide a secondary exit in the finished goods warehouse. Ensure that all exit doors open in the direction of evacuation. 4 Install a back-up system for the emergency alarm system and regularly check the alarm. 5. Install emergency lights throughout the corridors leading to the emergency exits and assembling point in production building #1 production building #2 and the boiler room in production building #2. 6. Provide new mesh metal cutting gloves as for cutting operators when the gloves are torn or damaged. Establish a system to track the use of Personal Protective Equipment (PPE) including measures to replace used or damaged PPE. 1. Arrange for a third-party to conduct a fire risk assessment. 2. Post evacuation maps with the correct layout of the evacuation routes in all areas of thebuilding. 3. Provide a secondary exit in the finished goods warehouse. Ensure that all exit doors open in the direction of evacuation. 4 Install a back-up system for the emergency alarm system and regularly check the alarm. 5. Install emergency lights throughout the corridors leading to the emergency exits and assembling point in production building #1 production building #2 and the boiler room in production building #2. 6. Provide new mesh metal cutting gloves as for cutting operators when the gloves are torn or damaged. Establish a system to track the use of Personal Protective Equipment (PPE) including measures to replace used or damaged PPE. |  | 1.Factory will conductfirerisk assessmentby accredited third party expert. 2.Factory will be places arrow sign marked on the floor in pressingand check all arrow signs then repaint.Factory will create evacuation map and posting in press area. 3.a.There is floor height difference between boiler/compressor room floor with finished goods areas floor that directly lies in front of boiler/compressor room and there is a door sill at boiler/compressor room that might trip workers when they&rsquore in a rush to exit. b. Even though the door on the second floor at building #1 from sample room toproduction swings outwards it directly opens to stairs without a platform which runs the risks of people who walk upstairs accidentally getting hit by a person who opens the door from the inside and exposes people who seek egress route from second floor to ground floor during emergency with fall hazard. c. Factory will repair floor and door at boiler /compressor room d. Factory willcheck and re layout the door and will choose sliding door or move the door to right place. 4.Emergencyalarmsinproductionbuilding#1andproductionbuilding#2areequippedwithUPS (Uninterrupted Power Supply) there is an UPS for each building. However there is no functionality test upon fire alarm as per manufacture standard to ensure fire alarm is still functioning during electrical black-out. There is no awareness that functionality test shall be made for its functionality and it should be as per manufacture standards.Factory willtestemergency alarmsevery 6 monthalongside fire drill training.Factory will connect emergency alarm to UPS and test functionality per manufacturer&rsquos suggested time frame.
| 14565 | HSE.1-Employers shall comply with all national laws regulations and procedures concerning health safety and the environment. | 5 - 1. There is no lifting belt provided for workers who involve lifting during performing their job such as warehouses workers. ER.1 HSE.7 2. There is no lighting level intensity inspection upon emergency light installed at the facility.HSE.13 3. The exit from the fabric warehouse at building #1 has been partially blocked and the exit sign is also not visible as it has been blocked by goods. HSE.5 4. All eight water tanks do not have the following labels: &ldquoConfined Space&rdquo and &ldquoDo not enter&rdquo. There is also no identification for each space. ER.1 5. Currently there are only 44 fire action officers and five fire coordinators while total employees at the factory is 1946 people. There should be at least 156 fire action officers and 20 fire coordinators for a factory of this size. HSE.1 0 | Provide workers who are involved in lifting with lifting belts and provide training. Emergency light shall be inspected at least once a month for 30 seconds and ensure that the emergency lights is set to provide an initital lighting of at least 10 lux and the lights along the emergency route is at least 1 lux when first turned on. Ensure every door is opened without any blockage and that exit signs are fully visible. Put labels and markings on the eight water tanks as &ldquoConfined Space&rdquo &ldquoDo not enter&rdquo and the identification. Ensure there are 156 fire action officers and 20 fire coordinators. Provide workers who are involved in lifting with lifting belts and provide training. Emergency light shall be inspected at least once a month for 30 seconds and ensure that the emergency lights is set to provide an initital lighting of at least 10 lux and the lights along the emergency route is at least 1 lux when first turned on. Ensure every door is opened without any blockage and that exit signs are fully visible. Put labels and markings on the eight water tanks as &ldquoConfined Space&rdquo &ldquoDo not enter&rdquo and the identification. Ensure there are 156 fire action officers and 20 fire coordinators. |  | 1. Factory has providedlifting belt andHSEtrainingtoworkerson November 2017 2. Factorywill conduct monthlyinspectionat least 30 seconds for emergency light and provide monitoring checklist 3.Factory has been include in 6S daily inspectionand 6S report sent to each department 4.Provide clear signage indicating &ldquoConfined Space&rdquoandsecure area with appropriate measures to prevent unauthorized entry. 5.a. Searching provider andprepare of proposal b. Create training schedule
| 14566 | HSE.1-Employers shall comply with all national laws regulations and procedures concerning health safety and the environment. | 8 - 1. The factory has not established a system to protect the reproductive health of employees through minimizing exposure to workplace hazards. In addition no lactation room is provided in the factory. HSE.12. 2. The factory does not establish proactive steps to reduce repetitive-motion stress/injuries. In addition the factory does not provide any ergonomic breaks. HSE.17 3. There are no Standard Operating Procedures (SOPs) for each job with a focus on performing the job safely. ER.31 4. The factory has not established safety procedures and guidance documents for external contractors/service providers concerning Health &amp Safety. ER.31 1. Finding Status: Partially Remediated Explanation: The factory has established procedures and systems to protect the reproductive health of breast-feeding workers and pregnant workers. However there is no procedure to protect the reproductive health of all workers such as disabled workers non-pregnant workers and male workers based on job hazards exposure. Furthermore there has been no lactation training conducted yet as per law to pregnant and lactating workers even though a lactation room has been provided near the new temporary fabric warehouse. HSE.12 Root Causes: There is no awareness that reproductive protection is not only about pregnant and breast- feeding workers but also protection to disabled workers non-pregnant workers and male workers. 2. Finding Status: Partially Remediated Explanation: Factory has procedures on ergonomics however there is no consistent implementation of this program since the procedures were created: HSE.17 There is no job rotation stretching and exercise implemented. The last ergonomic training on August 15 2016 was only conducted for 73 out of 1705 workers. No ergonomic break time during working hours established yet. Root Causes: There is a tight schedule of production which made HSE officers unable to schedule ergonomic training for all workers. Furthermore there is no approval for ergonomic break time job rotation stretching and exercise by upper level management. Hence these programs cannot be implemented yet by HSE officers. 3. Finding Status: Not Remediated Explanation: There are no Standard Operating Procedures (SOPs) for each job with a focus on performing the job safely established yet. ER.31 Root Causes: There is a misunderstanding regarding this matter since factory management thought that posting this information as a a general poster in the production areas instead of making it into Standard Operating Procedures (SOPs) for each job with a focus on performing the job safely. 4. Finding Status: Partially Remediated Explanation: The factory has already established safety procedures and guidance documents for external contractors/service providers concerning Health & Safety (RSK-P-HSE-011 issued on June 16 2016) however there is no actual implementation for contractor and service provider. ER.31 Root Causes: There is no written evidence maintained for every induction performed to contractors and service providers. |  |  | 1. Factory will create proceduretoprotectthedisabled workers non-pregnant workers and male workers based on job hazards exposure.Factory will create of training scheduleon reproductive health pregnant and lactatingworkers.Factory will posting health information related to worker health 2.There is no job rotation stretching and exercise implemented.The last ergonomic training on August 15 2016 was only conductedfor 73 out of 1705 workers.No ergonomic break time during working hours established yet.Factory will conduct refresh training for all workers and will have meeting with management regarding stretching and exercise implemented 3.Factory is currently reviewing all SOP&rsquos through HQ initiated SMART Project Team and will include updated ergonomics andjob safetyrequirements. 4.Factory willcommunicate established safety procedures and guidance documents for external contractors/service providers regarding H &amp S.Signature acknowledgement log will be established for contractors/service providers.
| 14567 | HOW.1.1-Employers shall comply with all national laws regulations and procedures concerning hours of work public holidays and leave. | 12 - 1. The workers are using finger scan time record system as a computerized electronic time record. However paper time cards of March 2015 for 10 sewing operators were found in the production area of building 1. According to management paper time cards were used temporary to record night shift. There were inconsistencies between the printed finger scan time records and paper time cards regarding the overtime hours in March 2015. In addition night shift hours from 8:00 PM to 7:30 AM and Sunday work were reflected in paper time cards of March 2015 for 5 to 9 days but there was no Sunday work and night shift reflected in the printed finger scan time records. ER.23 2. Printed time record of a sewing operator from line 11showed overtime hours 18 hours /week and 65 hours /month without night shift work in period and Sunday work. However the punch card showed overtime hours up to 37 hours/week and 101 hours /month and night shift in periods of March 9th to March 13th 2015 with Sunday work on March 22nd2015. ER.2 ER.23 3. Printed time record of a sewing operator from line B 9 (S15030023) showed overtime hours 19.5 hours /week and 78 hours /month but the punch card showed overtime hours 37 hours/week (March 16 to 22) and 84 hours /month and night shift in periods of March 16th to March 23rd 2015 with Sunday work on March 22nd2015. ER.2 ER.23 4. New workers use time cards instead of finger scan time record system for the first 3 days of their probation period. Additionally new workers in building 2 do not clock in and out their timecards by themselves since the time card machine broke down in building 2. The admin staff writes down a manual uniform time in and time out such as 07:30 to 16:30 in workers&rsquo time card. There were 23 new workers and 10 of them in building 2. ER.23 5. The working hours records do not contain identification of pregnant/lactating women. ER.23 HOW.5 1. Finding Status: Remediated Explanation: Based on document review management and worker interviews it is noted that all workers after passing probation period are using finger scan time record system as a computerized electronic time record. The probationary /trainees are using punch cards to record their working hours. There is no more practice of using two sets of time record systems for same worker. All overtime hours are recorded on time records accurately. 2. Finding Status: Remediated Explanation: Based on document review it is noted that all working hours including Sunday work are reflected on the computerized time records. 3. Finding Status: Remediated Explanation: Based on document review it is noted that all working hours including Sunday work is reflected on the computerized time records. 4. Finding Status: Remediated Explanation: Based on document review and worker interviews it is noted that new workers are provided with time cards during their five days of the probation period and all of them clock in and clock out their time cards by themselves. 5. Finding Status: Remediated Explanation: Based on document review it is noted that the working hours records includes identification of pregnant/lactating women. | 1. Ensure all working hours including 2nd shift hours excessive overtime and work done on Sunday are accurately recorded in one time record system. 2. Ensure new workers are provided with reliable time records from the 1st day they are hired. 1. Ensure all working hours including 2nd shift hours excessive overtime and work done on Sunday are accurately recorded in one time record system. 2. Ensure new workers are provided with reliable time records from the 1st day they are hired.
| 14568 | HOW.1.1-Employers shall comply with all national laws regulations and procedures concerning hours of work public holidays and leave. | 4 - 1. The factory provided computerized time records that do not actually reflect all overtime hours. The printed finger scan time records do not reflect all overtime hours and the factory includes overtime as a general practice into production planning. There were three cases of excessive overtime with more than 60 hours per week and workers not receiving a rest day for every 7-days period. HOW.2 2. Printed time records of a sewing operator from line 11 showed overtime hours 18 hours /week and 65 hours /month without night shift work in period and Sunday work. However the paper time card showed overtime hours up to 37 hours/week (total weekly hours: 77 hours consist of 40 regular plus 37 overtime hours) in the period from March 9 to March 13 2015 and Sunday work on March 22nd2015. HOW.1.3 3. Printed time record of a sewing operator from line B 9 showed overtime hours 19.5 hours /week and 78 hours /month. However the paper time card showed overtime hours 37 hours/week (total weekly hours: 77 hours consist of 40 regular plus 37 overtime hours) in period of March 16 to 22 2015 Sunday work on March 22nd2015. HOW.1.3 4. Based on separate paper time cards at least 10 workers from sewing section worked 13 consecutive days from March 16th to March 28th 2015 without a rest day. HOW.2 1. Finding Status: Remediated Explanation: Based on document review it is noted that all working hours are recorded on the time records accurately. 2. Finding Status: Not Remediated Explanation: Out of 45 selected sample workers it is noted that five workers from sewing section worked as much as 23 hours of overtime in one week (working a total of 63 hours including 40 regular hours) in July 2017 and fourteen workers from sewing ironing and maintenance sections worked as much as 5 hours of overtime in one day and up to 31 hours of overtime in one week (working a total of 71 hours including 40 regular hours and 2 rest day works-Saturday and Sunday) in June 2017. HOW.1.3 Root causes: There is a high rejection percentage of the finished goods therefore the sewing lines work overtime to do the repairs on the rejects. This affects processes after sewing like ironing hence several workers at ironing also work overtime. Maintenance also has to work overtime since they have to be alert when there is a damaged sewing machine during this overtime. If one sewing machine failed to function properly then it will affect the output and in the end will prolong lead time to finished goods shipment. 3. Finding Status: Not Remediated Explanation: Based on document review it is noted that workers worked daily and weekly excessive overtime hours in June and July 2017 more than three hours per day and 14 hours of overtime per week with weekly work hours up to 71 as above details. HOW.1.3 Root Causes: There is a high rejection percentage of the finished goods therefore the sewing lines work overtime to do the repairs on the rejects. This affects processes after sewing like ironing hence several workers at ironing also work overtime. Maintenance also has to work overtime since they have to be alert when there is a damaged sewing machine during this overtime. If one sewing machine failed to function properly then it will affect the output and in the end will prolong lead time to finished goods shipment. 4. Finding Status: 4. Not Remediated Explanation: Out of 45 selected sample workers it is noted that fourteen workers from sewing ironing and maintenance sections worked 11 to 13 consecutive days during the period of June 12 to June 22 2017 for ironing workers and period of June 5 2017 to June 16 2017 for sewing and maintenance workers. HOW.2 Root Causes: There is a high rejection percentage of the finished goods therefore the sewing lines work overtime to do the repairs on the rejects. This affects processes after sewing like ironing hence several workers at ironing also work overtime. Maintenance also has to work overtime since they have to be alert when there is a damaged sewing machine during this overtime. If one sewing machine failed to function properly then it will affect the output and in the end will prolong lead time to finished goods shipment. | 1. Ensure that workers do not work more than 60 hours per week including overtime. 2. Ensure that all workers receive at least one rest day in every 7-day period. 3. Ensure that overtime is not included in the regular production planning. 4. FLA affiliate Company&rsquos Sourcing and Social Compliance teams should: a) implement FLA Principles of Fair Labor and Responsible Sourcing and b) accordingly coordinate on the topics mentioned below to help the factory address its excessive hours issue: a. How to provide better order forecasts to the factoriesb. Possible workshops/consultancy for the factory on how to improve c. Clear guidelines on how to extend shipment deadlines in case of contingencies d. Steps that factory management must follow if overtime is inevitable (steps for how to communicate with the brand&rsquosSourcing and Social Compliance teams)e. Clear guidelines on the calculation and setting of reasonable production targets that will not demand work beyond regular working hours or during breaksf. Clear guidelines on how and when the factory can use subcontractors and/or temporary workers to avoid excessive overtime. 1. Ensure that workers do not work more than 60 hours per week including overtime. 2. Ensure that all workers receive at least one rest day in every 7-day period. 3. Ensure that overtime is not included in the regular production planning. 4. FLA affiliate Company&rsquos Sourcing and Social Compliance teams should: a) implement FLA Principles of Fair Labor and Responsible Sourcing and b) accordingly coordinate on the topics mentioned below to help the factory address its excessive hours issue: a. How to provide better order forecasts to the factoriesb. Possible workshops/consultancy for the factory on how to improve c. Clear guidelines on how to extend shipment deadlines in case of contingencies d. Steps that factory management must follow if overtime is inevitable (steps for how to communicate with the brand&rsquosSourcing and Social Compliance teams)e. Clear guidelines on the calculation and setting of reasonable production targets that will not demand work beyond regular working hours or during breaksf. Clear guidelines on how and when the factory can use subcontractors and/or temporary workers to avoid excessive overtime. |  | 2. Factorywill implement internal controls over excessive overtime. 3. Factorywill implement internal controls over excessive overtime 4. Factorywill implement internal controls over excessive overtime
| 14569 | XX.2-Please refer to the assessment report for benchmark information. For assessments conducted prior to 2020 benchmark numbers reflect the FLA’s 2011 Workplace Compliance Benchmarks. | 3 - 1. 1319 out of 1838 (71.76%) production workers are employed under the specified period of time contracts (PKWT) although they are working permanent jobs in the cutting sewing finishing and packing departments.This violates legal requirements that state that workers can only be hired under unlimited permanent contracts if they perform permanent jobs. ER.9 ER.11 2. New workers are required to undergo a three-day probation period before the factory provides them with a work agreement under the specified period of time contract (PKWT). In addition workers only receive the work agreement and the PKWT contract when they finish the probationary period violating local law stating that a work agreement for a specified period of time cannot stipulate a probation period. ER.7 3. According to management the factory does not employ any workers with disabilities violating local law that requires the factory to hire one person with disabilities per 100 employees. Thus for a factory with 1838 workers in total the factory has to hire at least 19 workers with disabilities as per legal requirements. However the factory has not established a program to hire workers with disabilities. ND.1 ND.2 4. The factory does not have policies and procedures for performance reviews that includes steps and processes demonstrates linkages to job grading prohibits discrimination provides written feedback and complies with legal requirements. ER.29.1 5. There are no procedures on raising or broadening skills in order to advance workers in their careers. The factory only conducts performance reviews for managerial staff but not for production workers. In addition the factory does not have procedures with steps and requirements regarding promotion demotion and reassignment scheme. ER.28 ER.30 1. Finding Status: Partially Remediated Explanation: Based on employment record the factory has gradually changed the status of production workers to permanent. However it is noted that 506 out of 1705 (29.67%) production workers are still employed under the specified period of time contracts (PKWT) although they are working permanent jobs in the cutting sewing finishing and packing departments. This still violates legal requirements that state that workers can only be hired under unlimited permanent contracts if they perform permanent jobs. ER.9 ER.11 Root Causes: This is an ongoing process that might take two years to complete the whole elevation of employment status from specified period time to permanent term. The factory management worries if there is not enough order they have to dismiss workers. If all the workers are in permanent employment the factory has to pay for a huge amount of severance payment. 2. Finding Status: Not Remediated Explanation: Based on document review management and worker interviews it is noted that new workers are still required to undergo probation or training period for up to 5 days before the factory provides them with a work agreement under the specified period of time contract (PKWT). In addition workers only receive the work agreement and the PKWT contract when they finish the probationary period while workers who do not pass probation period are terminated without any work agreement. Four out of 19 new workers in May 2017 and 15 out of 73 workers in 2017 did not pass the probation period violating local law stating that a work agreement for a specified period of time cannot stipulate a probation period. ER.7 Root Causes: There is misconception by HR department that probation can be applied to contracts for specific periods of time. HR who is responsible for issuing work agreement needs to have fix confirmation from end user (supervisor as direct superior) first before they issue the work agreement to the said worker while it usually takes 3 months for the end user to send any confirmation to HR department. 3. Finding Status: Partially Remediated Explanation: According to management the factory employs only one worker with disability violating local law that requires the factory to hire one person with disabilities per 100 employees. Thus for a factory with 1946 employees in total the factory has to hire at least 19 workers with disabilities as per legal requirements. The factory has not established a program to train and hire more workers with disabilities. ND.1 ND.2 Root Causes: Factory management is having difficulties finding disabled applicants since these types of applicants are rare. Furthermore the factory does not consider it urgent to meet the quota. As a result the factory does not initiatively contact any local institutions or NGO who connect with disabled persons to encourage them to apply to vacancies at the factory. 4. Finding Status: Partially Remediated Explanation: The factory has established procedures for performance reviews that includes steps and processes prohibits discrimination provides written feedback and complies with legal requirements. However there is no policy on performance review. The available procedure (RSK-P-HRD-010 issued on August 1 2016) stating performance review is conducted once every three months but in practice this occurs only once after the first three months and then another one after one year. The procedure does not included job grading. The implementation is not consistent as interview with workers showed that the performance reviews have not been consistent. ER.29.1 Root Causes: There is inadequate document organization since: Disorganized filing which has caused HR Department to misplace the related policy. There is no job grading established yet as a goal for conducted performance review. Also there is no responsible person appointed or designated to ensure procedures of Human Resource is implemented and properly reviewed or to revise as per regulation and actual implementation. Therefore there is no implementation of the established procedures. 5. Finding Status: Not Remediated Explanation: The factory has not established procedures on raising or broadening skills in order to advance workers in their careers. The factory has not established procedures with steps and requirements regarding promotion demotion and reassignment scheme. According to management there is procedure but it was made in Chinese language hence cannot be verified for the content. The factory has not conducted performance review for all workers. The performance review was conducted on for staff level cutting and sample workers in periods of December 2016 to May 2017. ER.28 ER.30 | 1. Ensure that all new workers that will perform permanent jobs receive permanent contracts. 2. Convert all workers that are currently hired under the PKWT contract but perform permanent jobs to permanent employee status as per legal requirements. Provide them with all seniority and other fringe benefits dating back to the hiring date of their first PKWT contract as per FLA benchmarks and local law requirements. 3. Provide all workers with a work agreement and contract regardless of them passing the probation period. Provide the work agreement and contract on the first day of hire as per legal requirements. 1. Ensure that all new workers that will perform permanent jobs receive permanent contracts. 2. Convert all workers that are currently hired under the PKWT contract but perform permanent jobs to permanent employee status as per legal requirements. Provide them with all seniority and other fringe benefits dating back to the hiring date of their first PKWT contract as per FLA benchmarks and local law requirements. 3. Provide all workers with a work agreement and contract regardless of them passing the probation period. Provide the work agreement and contract on the first day of hire as per legal requirements. |  | 1.a. Per November 21 2017 Factory still have 584 workers that are still employed under the specified period of time. Factory already make a schedule for permanent procedure base on the 2 times of contract period. The 1stcontract period is for 3 months and the second contract is for 1 year and permanent process on the ending. We have divided the permanent process into 5 quarters and will be fully achieve on the 1stquarter of 2019 (February 2019).( see the attachment for detail planning ) 2.a.According to our current condition our garment products have a high quality standard compare to other factories.Factory need to assure the new recruits for production have the standard sewing skills that we needed. b. We implement 3 days skill test period in the separate place from production. We put them in the specific line in the technical department and monitor by technical and HR department. After 3 days skill test period HR will allocate the candidate who pass the test to user. Candidates who are fail are paid according to regulation: basic salary / 21 days. c. No skill test needed for nonproduction. After the interview by HR and user candidate will be recruited and sign the 1stcontract of 3 months. 3.a. Factory will expand our recruitment radius. b.Factory willmake all reasonable effort createvacancy for person with disabilities. c.Factory will also cooperate with Local Manpower Office to help and provide us the disable persons. 4.a.Management will review and approvecurrent procedure base on our actual condition and we willtrain workers onthe new standard. b. Every six months HR will review all of the procedures to make sure that those documents are currentand updated.
| 14570 | XX.4-Please refer to the assessment report for benchmark information. For assessments conducted prior to 2020 benchmark numbers reflect the FLA’s 2011 Workplace Compliance Benchmarks. | 10 - The factory has not developed policies and procedures on review process to ensure updates are made according to local law and FLA Workplace Code requirements. As a result the factory management does not periodically review its policies and procedures for all Employment Functions such as Recruitment Hiring &amp Personnel Development Compensation Workplace Conduct &amp Discipline Grievance System Environmental Protection Termination &amp Retrenchment Industrial Relations &amp Freedom of Association and Health &amp Safety. ER.1.3 ER.25.2 ER 31.2 and ER.32.5 1. Finding Status: Not Remediated Explanation: Based on document review and management interview it is noted that the factory has not developed policies and procedures on review process to ensure updates are made according to local law and FLA Workplace Code requirements. As a result factory management does not periodically review its policies and procedures for all Employment Functions. ER.1.3 ER.25.2 ER 31.2 and ER.32.5 Root Causes: The policy and procedure has just recently been established and approved by management. Hence they do not think it is necessary to establish procedures for review yet. |  |  | 1a.Factory will create procedure document control 1b. Factory will review and updateprocedure &amp policiesannually 1c. Factory will postannually updatedpolicies &amp procedure at announcement board
| 14571 | XX.3-Please refer to the assessment report for benchmark information. For assessments conducted prior to 2020 benchmark numbers reflect the FLA’s 2011 Workplace Compliance Benchmarks. | 9 - 1. Supervisors do not receive specific training on the following Employment Functions: Recruitment Hiring &amp Personnel Development Compensation Hours of Work Termination &amp Retrenchment Industrial Relations &amp Freedom of Association workplace conduct grievance system. ER.17.1 2. The orientation training for new workers only lasts 90 minutes. This orientation training is insufficient since it barely gives adequate information to workers and does not cover all Employment Functions such as Grievance System and Industrial Relations &amp Freedom of Association. In addition workers do not receive written documentation that substantiates all the issues covered in orientation ER.15.3 3. There is no ongoing training to employees on the following Employment Functions: Recruitment Hiring &amp Personnel Development and Termination &amp Retrenchment. ER.28. 4. The factory does not communicate the recruitment hiring and personnel development policies and procedures and their updates to the general workforce. ER.28 5. The disciplinary procedures do not include the presence of a third-party witness during application of disciplinary actions. ER.27.4 1. Finding Status: Partially Remediated Explanation: Based on the training records it is noted that only 22 out of 48 supervisors have been trained on August 10 2016 on Recruitment Hiring Compensation Hours of Work Termination & Retrenchment. While the material has not included Freedom of Association Workplace Conduct and Grievance system. ER.17.1 Root Causes: 26 supervisors were unable to attend the training due to the tight production schedule. Supervisors are mainly responsible for ensuring that daily outputs meet the set target therefore they do not see the training as a priority. Written procedure for grievance and workplace conduct has been posted on the notice board. Therefore HR does not see the necessity to include it again during the training. Since there is no union at the factory Freedom of Association is not included in the training material. Also the factory does not want to encourage their supervisors to form any union since there is already a Bipartite institution as a communication forum between factory management and worker representatives. 2. Finding Status: Partially Remediated Explanation: Based on training records it is noted the orientation training has been conducted for 2 to 3 hours. However training material did not include Grievance System & Freedom of Association and no evidence that training material has been provided in copy for each attendee. 4 out of 12 new workers stated that they did not receive a copy of their training materials. ER.15.3 Root Causes: The HR department who responsible in creating and communicate training materials consider since there has been grievance procedure posted on announcement board then it is suffice. While no Freedom of Association included during induction since factory does not want to encourage new worker to form union in factory. The HR department missed this out and forgot to document or ask attendees to sign when they receive training material. 3. Finding Status: Not Remediated Explanation: Based on management interview it is noted that the factory has not provided ongoing training to employees on Recruitment Hiring & Personnel Development and Termination & Retrenchment. ER.28.1 Root Causes: There is misconception by factory management that Recruitment Hiring & Personnel Development and Termination & Retrenchment is domain of HR department and not workers therefore there is no need to train workers regarding these matters. 4. Finding Status: Not Remediated Explanation: The factory has not communicated the Recruitment Hiring and Personnel Development policies and procedures and their updates to the general workforce. ER.28 Root Causes: There is misconception by factory management that Recruitment Hiring & Personnel Development and Termination & Retrenchment is in the domain of HR department and not workers therefore there is no need to train workers regarding these matters. The factory has a top-down management style in other words all decisions come from management level to workers without any opportunity for workers to give suggestion or raise concerns. 5. Finding Status: Not Remediated Explanation: Based on document review it is noted the current disciplinary procedures RSK-P-HRD-011 issued on November 1 2016 has not included the presence of a third-party witness during application of disciplinary actions. ER.27.4 Root Causes: The factory management does not recognize workers’ right to summon or have present any witness. Furthermore HR does the investigation before issuing disciplinary actions therefore it is not necessary for workers to have witnesses on their side. |  |  | 1.Create schedule of refresh training for allworkers training willincludeRecruitmentHiringCompensation HoursofWorkTerminationRetrenchment freedom of association workplace conduct and grievance system. 2. a.Training schedulewill includeGrievance &amp Freedom ofAssociation. b. ThematerialtrainingregardingRecruitment Hiring Compensation Hours of work Termination Retrenchment Grievance &amp Freedom of association ) and already provide in copy for each attendee starting on November 6.Signature acknowledgement log book to be created for workers confirming receipt of training material. 3.a.Factory will conduct refresh trainingandincludeRecruitmentHiringCompensation HoursofWorkTerminationRetrenchment freedom of association workplace conduct and grievance systemtoSupervisorsTeam and Sectionleaders admin and operators. 4. a.Review and update policies &ampprocedure b. Create procedure control document c. Create schedule for socialization policies &amp procedure d. Create internal audit schedule for labor and HSE 5. a.Thefactory management has been revised the procedure of undisciplined In practical factory already includethe witness during process of undisciplined actions.Witness will interview by HRall information from workers and witness willmentioned inBAP (Berkas Acara Perkara) and base on witness and otherresult investigationHRwill give verbal warning or warning letter.Warning letter will be signed by workers HR and superiorsHR will createsummarymonthlyreport for undisciplined caseand forwardto alldepartment head.
| 14572 | XX.5-Please refer to the assessment report for benchmark information. For assessments conducted prior to 2020 benchmark numbers reflect the FLA’s 2011 Workplace Compliance Benchmarks. | 11 - 1. The factory does not communicate its policies and procedures on all Employment Functions to the general workforce. 2. The worker integration component is missing for all Employment Functions. The factory has not established procedures for receiving worker input/feedback on the creation implementation and revision of its policies and procedures. Workers are neither systematically integrated nor consulted in the decision-making processes. 1. Finding Status: Remediated Explanation: Based on document review observation and worker interview it is noted that the policies and procedures regarding all Employment Functions have been communicated to the general workforce by being posted on announcement board. 2. Finding Status: Not Remediated Explanation: Based on document review and management interview it is noted that the worker integration component is still missing for all Employment Functions. Workers are neither systematically integrated nor consulted in the decision-making processes. ER.1.3 ER.29 ER.30 Root Causes: The factory has not established procedures for receiving worker input/feedback on the creation implementation and revision of its policies and procedures. |  |  | 1.a. FactoryManagementwill reviseand approvethe current procedure base on our actual condition and we will socialize the new standard toallemployees. 1b. Factory will create procedure control document to make sure that those document arecurrent and updatedwith our current condition.